# Proceso de negocio del macroproceso estratégico

P&Pmis Construction AI. Capital Portfolio & Investment Governance. Corte del 14 de octubre de 2026.

Este documento describe cómo se prepara, compara, desarrolla y decide una inversión. Distingue las dependencias obligatorias de las actividades paralelas o condicionales y conserva las autoridades de cada dominio.

La aceptación de negocio requiere firmas de representantes autorizados. Una prueba técnica aprobada o un inventario de código no constituye esa aceptación.

# Objetivo y principios

ADMIN configura tipos, taxonomías, políticas, umbrales, herencia, numeración, permisos y publicación reutilizables. USER opera instancias Workspace, registros, evaluaciones, escenarios y decisiones con permisos acotados al contexto.

El orden de navegación ayuda a encontrar la siguiente actividad, pero no sustituye la elegibilidad del backend. Una recomendación Portfolio, un escenario congelado, evidencia READY y una decisión FID son objetos de negocio diferentes.

# Mapa del proceso y condiciones de secuencia

| Fase | Ámbito | Relación de negocio |
| --- | --- | --- |
| 1 | Enterprise y Workspace | Configurar primero; crear y operar después. Materializar Project solo en el punto autorizado. |
| 2 | Capital Planning y origination | Demand, Idea y evaluación; BA cuando aplique; Proposal y Strategic Gate. |
| 3 | Portfolio y escenarios | Intake, evaluación y análisis; Budget y Resources pueden elaborarse en paralelo antes de Convergence y Review. |
| 4 | Business Case e inversión | Five Case reúne fuentes de Benefits, Commercial, FEL/PDRI, Basic Data, Risk/Permit, Capability, Funding y FIN. |
| 5 | QRA contextual | Foundation y resultados Cost/Schedule únicamente cuando corresponda por política y capacidad soportada. |
| 6 | Gate y decisión | Preparar evidencia, verificar fuentes/criterios, congelar paquete y someterlo a Gate07K. |
| 7 | Post FID | Evaluar condiciones, bloqueos y elegibilidad. Detenerse antes de ejecución operacional. |

MANDATORY PREDECESSOR exige una salida previa dentro de la ruta indicada. RECOMMENDED PREDECESSOR orienta sin crear bloqueo. PARALLEL-CAPABLE permite avanzar actividades compatibles. CONDITIONAL depende de política, tipo o contexto. OPTIONAL no se transforma en requisito universal.

# Capital Owner desde origen hasta FID

La ruta de referencia usa una inversión de expansión de procesamiento de cobre y taxonomía realmente configurada. Idea es un registro estratégico. Después de evaluación y, cuando aplique, Business Analysis independiente, Proposal llega a Strategic Gate. APPROVE habilita el handoff READY_FOR_PORTFOLIO_INTAKE, no constituye FID.

ProjectCreationService.materialize crea la identidad EnterpriseWorkspace de tipo PROJECT después de aprobar la solicitud. La instancia comienza pending. Portfolio Membership, definición, evidencias y autorizaciones no se sustituyen por una activación anticipada.

Budget y Resources producen alternativas estratégicas. Scenario Convergence recomienda una alternativa viable y Periodic Portfolio Review registra conclusiones y solicitudes de gobernanza. La recomendación no decide formalmente la inversión.

Five Case mantiene Strategic, Economic, Commercial, Financial y Management con referencias gobernadas. FEL es etapa; PDRI es madurez. Funding conserva fuentes, fondos y asignaciones separadas del Budget. FIN calcula el caso determinístico sin modificar Treasury/Accounting.

Cuando la política lo requiere, QRA usa un modelo APPROVED_FOR_ANALYSIS y un resultado ACCEPTED actual, compatible con analysis type y scope. Gate07J captura evidencias y criterios. Solo Gate07K con actor autorizado e independiente decide GO, HOLD, RECYCLE o KILL. PYP-FFA más GO establece FID y autorización de inversión/fondos completos, sin activar Project automáticamente.

Esta descripción es el recorrido de uso. La cobertura A0 a A31 debe evaluarse como una ejecución integrada; varias pruebas parciales o históricas no equivalen a una demostración completa fresca.

# Rutas Contractor Delivery y Direct Internal

CONTRACTOR_DELIVERY parte de una fuente contractual o necesidad de entrega gobernada. La autorización de fuente considera mobilization_authorized o notice_to_proceed_date. Sigue Project Creation, Initialization y Activation independiente. No se fuerza por defecto por Idea, Portfolio, FEL, Funding, QRA o FID.

DIRECT_INTERNAL usa su fuente de autorización interna y authorization_approved. Mantiene creación, inicialización y activación como controles separados. La política explícita puede añadir requisitos contextuales sin convertirlo silenciosamente en Capital Owner.

# Matriz de trazabilidad y autoridades

## Enterprise Workspace Governance

### P01 Reusable Workspace Types hierarchy numbering

Governance configuration → Published reusable configuration. Prerrequisito ADMIN: Published type/hierarchy/Record Code/numbering policy. Transacción: ADMIN reusable preparation.

Autoridad: Enterprise Administrator. Siguiente: P02. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P02 Live Enterprise Business Unit Portfolio instances

Instance fields → Canonical Workspace hierarchy. Prerrequisito ADMIN: P01 published taxonomy and parent rules. Transacción: Enterprise structure and Workspace context.

Autoridad: Enterprise Administrator. Siguiente: P03. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P03 Enterprise Explorer and Workspace Context

Scoped identity → Read-only shared context. Prerrequisito ADMIN: Authorized live Workspace. Transacción: Enterprise structure and Workspace context.

Autoridad: Read-only Executive. Siguiente: P04. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P13 Strategic Project Planning Entry

Strategic decision / template / manager → Shared ProjectCreationRequest CAPITAL_OWNER. Prerrequisito ADMIN: APPROVE current decision/readiness hashes, template and parent. Transacción: Project Workspace creation and initialization timing.

Autoridad: Investment / Project Manager. Siguiente: P14. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P14 Governed request approval and materialization

Approved creation request → One canonical pending Project identity. Prerrequisito ADMIN: Published source policy; independent approval. Transacción: Project Workspace creation and initialization timing.

Autoridad: Investment / Project Manager. Siguiente: P16. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P15 Project Workspace Initialization

Pending identity and checklist → Initialized state and eligibility; capital activation authorization may block. Prerrequisito ADMIN: Materialized Project; exact template/manager/modules/source context. Transacción: Project Workspace creation and initialization timing.

Autoridad: Project Workspace Initializer. Siguiente: P42. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P42 Independent Project Workspace Activation

Governed source authorization/checklist → Active canonical Project; stop before operational delivery. Prerrequisito ADMIN: Initialized eligible Project; source execution authorization; actor not initializer. Transacción: Post-FID Governance and operational boundary.

Autoridad: Project Workspace Activator. Siguiente: STOP_OPERATIONAL_BOUNDARY. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

## Strategic Capital Planning

### P04 Capital Planning Cycle

Horizon/scope/currency → OPEN cycle. Prerrequisito ADMIN: Capital Planning policy and published theme catalog. Transacción: Strategic capital demand, cycles, buckets and allocation.

Autoridad: Capital Planning Administrator. Siguiente: P05. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P05 Strategic Capital Demand

Need/sponsor/themes/objectives/value range → ENDORSED demand / optional Idea origin. Prerrequisito ADMIN: OPEN cycle and effective demand policy. Transacción: Strategic capital demand, cycles, buckets and allocation.

Autoridad: Project Sponsor. Siguiente: P08. Dependencia: OPTIONAL. Mandatory only in the stated route/context; not a requirement for all governance models.

### P06 Capital Buckets and Allocation Targets

Cycle/buckets/targets → Governed Target position. Prerrequisito ADMIN: ADMIN bucket taxonomy; USER allocation plan policy. Transacción: Strategic capital demand, cycles, buckets and allocation.

Autoridad: Portfolio Manager. Siguiente: P07. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P07 Target Current Recommended Approved positions

Frozen/current governed sources → Comparable positions without auto-approval. Prerrequisito ADMIN: Actual membership, recommendation and formal decision authority. Transacción: Strategic capital demand, cycles, buckets and allocation.

Autoridad: Portfolio Manager. Siguiente: P21. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

## Investment Origination

### P08 Idea origination and intake

Need/objectives/scope → Submitted/screened owned Idea. Prerrequisito ADMIN: Published Idea policy; eligible enterprise/business-unit/portfolio. Transacción: Idea, evaluation and governed Business Analysis.

Autoridad: Investment Originator. Siguiente: P09. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P09 Idea Evaluation and acceptance

Ratings/evidence → Immutable evaluation and ACCEPTED Idea. Prerrequisito ADMIN: Published evaluation matrix and assigned owner. Transacción: Idea, evaluation and governed Business Analysis.

Autoridad: Project Sponsor. Siguiente: P10. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P10 Business Analysis and alternatives

Accepted Idea/actual alternatives → Independently COMPLETED BA / READY_FOR_PROJECT_PROPOSAL. Prerrequisito ADMIN: Required by effective/snapshotted Idea governance policy. Transacción: Idea, evaluation and governed Business Analysis.

Autoridad: Investment / Project Manager. Siguiente: P11. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P11 Project Proposal

Scope/benefits/ROM/risks → READY_FOR_STRATEGIC_GATE stored; readiness READY_FOR_STRATEGIC_GATE_DECISION. Prerrequisito ADMIN: Accepted eligible Idea and required current BA. Transacción: Project Proposal.

Autoridad: Project Sponsor. Siguiente: P12. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P12 Strategic Gate Decision

Reviewed proposal snapshot → APPROVE→READY_FOR_PORTFOLIO_INTAKE. Prerrequisito ADMIN: Proposal ready and authority/committee configuration. Transacción: Strategic Gate.

Autoridad: Investment Committee / Decision Maker. Siguiente: P13. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

## Portfolio Planning Review

### P16 Portfolio Intake and Membership

Project and target portfolio → ACTIVE contextual membership. Prerrequisito ADMIN: Materialized capital planning entry. Transacción: Portfolio Intake and membership.

Autoridad: Portfolio Manager. Siguiente: P17. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P17 Evaluation and Prioritization

Contextual ratings → Immutable evaluation and Portfolio Rank. Prerrequisito ADMIN: ACTIVE eligible membership; effective criteria. Transacción: Evaluation and Prioritization.

Autoridad: Portfolio Manager. Siguiente: P18. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P18 Portfolio Analysis Investor Map Scorecard

Analysis source dataset → Branch readiness / map / scorecard. Prerrequisito ADMIN: Current evaluation/rank and analysis configuration. Transacción: Portfolio Analysis / Investor Map / Scorecard.

Autoridad: Portfolio Manager. Siguiente: P19/P20. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P19 Budget Target and Budget Scenarios Waterline

Published target/selection/time phasing → FROZEN analytical Budget Scenario. Prerrequisito ADMIN: Current analysis/currency compatible target policy. Transacción: Budget Planning and scenarios.

Autoridad: Cost / Finance Reviewer. Siguiente: P21. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P20 Capacity Demand and Resource Scenarios

Strategic capacity/demand → FROZEN Resource Scenario / overloads. Prerrequisito ADMIN: Current analysis and real published role-period capacity/demand. Transacción: Resource Planning and scenarios.

Autoridad: Project Controls. Siguiente: P21. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P21 Scenario Convergence and Recommendation

Compatible branch scenarios → Governed recommendation, not FID. Prerrequisito ADMIN: Required frozen branches under effective configuration. Transacción: Scenario Convergence and Recommendation.

Autoridad: Portfolio Manager. Siguiente: P22/P23/P36. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P22 Periodic Portfolio Review and Governance Actions

Snapshot / matrix / conclusions → Immutable completed review and request-only actions. Prerrequisito ADMIN: Effective review configuration and required actual sources. Transacción: Periodic Portfolio Review / actions.

Autoridad: Portfolio Manager. Siguiente: P23/P36. Dependencia: RECOMMENDED PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

## Business Case Investment Development

### P23 Five Case Business Case

Strategic/Economic/Commercial/Financial/Management → Current completed BC revision and governed source/hash bundle. Prerrequisito ADMIN: Capital Project, proposal/BA and applicable actual sources. Transacción: Five Case Business Case.

Autoridad: Investment / Project Manager. Siguiente: P37. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P24 Strategic Benefits Plan Register

Benefits/owners/measures → Completed Benefits evidence. Prerrequisito ADMIN: Effective Benefits policy and objective/source context. Transacción: Strategic Benefits.

Autoridad: Project Sponsor. Siguiente: P23/P37. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P25 Commercial Contracting Strategy

Delivery/packaging/contracting/risk allocation → Completed commercial evidence. Prerrequisito ADMIN: Effective framework and real source context. Transacción: Commercial & Contracting Strategy.

Autoridad: Commercial Reviewer. Siguiente: P23/P37. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P26 FEL Stage lifecycle

Stage-specific definition work → Governed ProjectFELStatus / FEL stage. Prerrequisito ADMIN: Published configured framework and Project definition readiness. Transacción: FEL and Definition Maturity / PDRI-compatible assessment.

Autoridad: Technical Assurance / FEL Reviewer. Siguiente: P27. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P27 Definition Maturity PDRI compatible assessment

Element scores/blocking gaps/actions → Immutable completed maturity evidence. Prerrequisito ADMIN: Configured current FEL stage assessment. Transacción: FEL and Definition Maturity / PDRI-compatible assessment.

Autoridad: Technical Assurance / FEL Reviewer. Siguiente: P23/P37. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P28 Basic Data Readiness

Availability/validation/quality/confidence/freshness → Exact denominator readiness / blockers. Prerrequisito ADMIN: Stage-aware published requirements. Transacción: Basic Data Readiness.

Autoridad: Project Controls. Siguiente: P23/P37. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P29 Risk Capacity Appetite Thresholds

Reusable governance framework → Effective USER risk context, not decision. Prerrequisito ADMIN: Published scope/date/contextual declarative risk policy. Transacción: Risk Governance effective context.

Autoridad: Risk Reviewer. Siguiente: P30. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P30 Risk Readiness

Exposure/owners/treatment/acceptance → Current completed Project/set Risk evidence. Prerrequisito ADMIN: Published readiness policy and actual risks. Transacción: Risk Readiness.

Autoridad: Risk Reviewer. Siguiente: P23/P37. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P31 Permit Readiness

Applicability/status/expiry/conditions → Current contextual Permit evidence. Prerrequisito ADMIN: Applicable requirement catalog and actual permits/conditions. Transacción: Permit Readiness.

Autoridad: Investment / Project Manager. Siguiente: P23/P37. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P32 Owner Capability Readiness

Maturity/quality/confidence/gaps/mitigations → Current Owner Capability evidence. Prerrequisito ADMIN: Effective capability framework and real accountability evidence. Transacción: Owner Capability Readiness.

Autoridad: Project Sponsor. Siguiente: P23/P37. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P33 Funding Source Fund Assignment Readiness

Confirmed eligible monetary assignments → Governed Funding coverage/snapshot. Prerrequisito ADMIN: Published Funding policy; actual funding authority. Transacción: Funding.

Autoridad: Cost / Finance Reviewer. Siguiente: P34/P37. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P34 Deterministic Economic Financial Model

Cashflows/capital structure/WACC → Completed FIN metrics/hash and reconciliation. Prerrequisito ADMIN: Applicable model configuration; actual BC/Budget/Funding sources. Transacción: Economic / Financial Model.

Autoridad: Cost / Finance Reviewer. Siguiente: P23/P37. Dependencia: PARALLEL-CAPABLE. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P35 QRA Foundation and approved Model Definition

Ranges/distributions/correlations/scope → APPROVED_FOR_ANALYSIS model; no simulation. Prerrequisito ADMIN: Methodology, actual sources and capability matching context. Transacción: QRA Foundation.

Autoridad: QRA Analyst. Siguiente: P36. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P36 Cost and or Schedule QRA results

Real run and independent acceptance → Accepted current bounded QRA provider evidence. Prerrequisito ADMIN: Approved current supported model; effective policy context. Transacción: Contextual QRA Results.

Autoridad: QRA Analyst. Siguiente: P23/P37. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

## Investment Gate Decision

### P37 Investment Gate Preparation Evidence Matrix Criteria

Scoped Class A/B/C evidence and criteria → READY package, not decision. Prerrequisito ADMIN: Recommendation/profile/effective policy; actual required providers. Transacción: Gate Preparation / Evidence / Decision Criteria.

Autoridad: Gate Preparer. Siguiente: P38. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P38 Source consistency and readiness verification

BC/native provider refs and hashes → Consistent exact scope/current evidence or controlled blockers. Prerrequisito ADMIN: Effective configured consistency/criteria rules. Transacción: Business Case ↔ Gate source consistency.

Autoridad: Gate Preparer. Siguiente: P39. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P39 Independent Gate package freeze

Policy/provider/source hashes, criteria and warnings → Immutable FROZEN package. Prerrequisito ADMIN: Current READY preparation; independent reviewer. Transacción: Freeze Gate package.

Autoridad: Gate Preparer. Siguiente: P40. Dependencia: MANDATORY PREDECESSOR. Mandatory only in the stated route/context; not a requirement for all governance models.

### P40 Formal Investment Decision FID

Decision checklist and authorized outcome/amount → DECIDED; PYP-FFA+GO formal FID only. Prerrequisito ADMIN: Frozen valid package, configured independent authority/SoD. Transacción: Investment Decision / FID.

Autoridad: Investment Committee / Decision Maker. Siguiente: P41. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

## Post FID Governance

### P41 Post FID conditions routing and eligibility

Decision/project state/conditions → Immutable per-project eligibility; no operational execution. Prerrequisito ADMIN: Formal decided FID and effective policy. Transacción: Post-FID Governance and operational boundary.

Autoridad: Post-FID Governance User. Siguiente: P15/P42. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

## Compact alternative routes

### P43 Contractor Delivery creation route

CONTRACT_AWARD request → Pending→initialized→active without default capital governance. Prerrequisito ADMIN: Contract source policy/template/manager; client/contract/scope/mobilization. Transacción: CONTRACTOR_DELIVERY compact creation→initialization→activation.

Autoridad: Investment / Project Manager. Siguiente: P14/P15/P42. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

### P44 Direct Internal creation route

DIRECT_AUTHORIZATION request → Pending→initialized→active without default capital governance. Prerrequisito ADMIN: Direct policy/template/manager; authorization/sponsor/approval. Transacción: DIRECT_INTERNAL compact creation→initialization→activation.

Autoridad: Investment / Project Manager. Siguiente: P14/P15/P42. Dependencia: CONDITIONAL. Not an artificial global sequence. Effective configuration/policy controls applicability and required evidence; source revisions may evolve iteratively.

# RACI por proceso

R es quien ejecuta, A quien responde por la aprobación, C quien se consulta e I quien se informa. Es una propuesta de responsabilidades derivada del modelo de permisos, no una delegación organizacional ni una firma de aceptación. Las concesiones reales siguen acotadas por tenant, Workspace y vigencia.

| ID | R | A | C e I |
| --- | --- | --- | --- |
| P01 | Enterprise Administrator | Independent configured publisher | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P02 | Enterprise Administrator | Enterprise Administrator | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P03 | Read-only Executive | Read-only Executive | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P04 | Capital Planning Administrator | Capital Planning Administrator | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P05 | Project Sponsor | Project Sponsor | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P06 | Portfolio Manager | Portfolio Manager | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P07 | Portfolio Manager | Portfolio Manager | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P08 | Investment Originator | Independent Business Analysis Reviewer where BA required | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P09 | Project Sponsor | Independent Business Analysis Reviewer where BA required | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P10 | Investment / Project Manager | Independent Business Analysis Reviewer where BA required | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P11 | Project Sponsor | Configured Proposal reviewer / owner authority | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P12 | Investment Committee / Decision Maker | Strategic Gate Decision Maker | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P13 | Investment / Project Manager | Independent Project Approver / Activator as applicable | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P14 | Investment / Project Manager | Independent Project Approver / Activator as applicable | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P15 | Project Workspace Initializer | Independent Project Approver / Activator as applicable | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P16 | Portfolio Manager | Portfolio Manager | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P17 | Portfolio Manager | Portfolio Evaluator | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P18 | Portfolio Manager | Portfolio Manager | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P19 | Cost / Finance Reviewer | Cost / Finance Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P20 | Project Controls | Project Controls | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P21 | Portfolio Manager | Portfolio Manager | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P22 | Portfolio Manager | Independent Portfolio Review approver | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P23 | Investment / Project Manager | Independent Business Case Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P24 | Project Sponsor | Independent Benefits Plan Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P25 | Commercial Reviewer | Independent Commercial Strategy Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P26 | Technical Assurance / FEL Reviewer | Independent FEL Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P27 | Technical Assurance / FEL Reviewer | Independent FEL Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P28 | Project Controls | Independent Basic Data Validator / Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P29 | Risk Reviewer | Risk Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P30 | Risk Reviewer | Independent Risk Acceptance Authority where required | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P31 | Investment / Project Manager | Configured Permit Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P32 | Project Sponsor | Independent Owner Capability Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P33 | Cost / Finance Reviewer | Independent Funding Approver | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P34 | Cost / Finance Reviewer | Independent FIN Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P35 | QRA Analyst | Independent QRA Model Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P36 | QRA Analyst | Independent QRA Result Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P37 | Gate Preparer | Independent Investment Evidence Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P38 | Gate Preparer | Gate Preparer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P39 | Gate Preparer | Independent Investment Evidence Reviewer | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P40 | Investment Committee / Decision Maker | Authorized independent Investment Decision Maker / Committee | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P41 | Post-FID Governance User | Configured Post-FID authority / independent Activator | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P42 | Project Workspace Activator | Configured Post-FID authority / independent Activator | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P43 | Investment / Project Manager | Independent Project Approver and Activator | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |
| P44 | Investment / Project Manager | Independent Project Approver and Activator | C: Project Sponsor; Project Controls; Relevant domain reviewer I: Read-only Executive |

# Evidencia gobernada y conservación histórica

Class A requiere la fuente nativa gobernada. Un adjunto manual no sustituye un provider obligatorio. El paquete congelado conserva revisión de política, fuentes, hashes, aplicabilidad, readiness, advertencias y criterios. Una nueva publicación o una fuente actual obsoleta no reescribe el historial congelado.

# Límite posterior al FID

El alcance termina en la gobernanza posterior al FID y en la elegibilidad de inicialización y activación. No incluye Project Delivery, ejecución de compras, construcción, pagos, contabilidad, tesorería, operación de activos ni realización operativa de beneficios. QRA integrado y QRA avanzado no se liberan.