## 01_Requirements
Requisitos AWP readiness y 4D
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
ID | Requisito | Resultado | Verificación
B1-01 | Existing O1B-B Schedule behavior preserved | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-02 | No Schedule rebuild | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-03 | CWA as area/container | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-04 | EWP | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-05 | PWP | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-06 | CWP | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-07 | IWP | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-08 | TWP | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-09 | SUPPORT configurable | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-10 | LOGISTICS configurable | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-11 | Scope ↔ Package M:N | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-12 | Plan ↔ Package M:N | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-13 | Package ↔ Activity M:N | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-14 | Package dependencies | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-15 | No rigid false AWP hierarchy | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-16 | ExecutionConstraint separate from P6 ScheduleConstraint | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-17 | Constraint types governed | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-18 | Blocking/nonblocking | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-19 | Constraint evidence/history | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-20 | Readiness assessment | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-21 | Workfront Readiness | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-22 | READY ≠ RELEASED | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-23 | Scheduled ≠ Ready | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-24 | Constraint does not silently change CPM logic | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-25 | Package mapping does not rewrite Schedule Version | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-26 | 4D Model | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-27 | Accepted Current source | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-28 | Approved Baseline source | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-29 | Baseline vs Current | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-30 | Data Date view | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-31 | INSTALL 4D semantics | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-32 | REMOVE 4D semantics | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-33 | TEMPORARY 4D semantics | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-34 | MAINTENANCE 4D semantics | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-35 | Plan/Package/Activity M:N works in 4D | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-36 | Derived 3D reused | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-37 | Original IFC unchanged | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-38 | Scope Baseline unchanged | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-39 | Schedule Baseline unchanged | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-40 | 4D filters | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-41 | 4D traceability | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-42 | Readiness/blocker overlay | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-43 | No native CPM engine | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-44 | No P6 API sync | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-45 | No duplicate Scope authority | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-46 | No duplicate Schedule authority | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-47 | ADMIN/USER separation | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-48 | RBAC | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-49 | SoD | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-50 | ETag | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-51 | Idempotency | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-52 | Audit | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-53 | PostgreSQL tests | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-54 | Chromium UAT | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-55 | Project 14 unchanged | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-56 | 0 open S1 | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes
B1-57 | 0 open S2 | PASS | Pruebas PG y políticas, regresión, Chromium, preservación y hashes

## 02_CWA
Áreas de construcción
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_cwa_container_hierarchy_and_cycle_etag | PASS | 36.132 | postgres-junit.xml
TC-2 | test_all_required_filter_dimensions_real_source[cwa_id] | PASS | 1.215 | postgres-junit.xml
TC-3 | AWP canonical project presentation has separate CWA/packages/execution constraint/readiness navigation and no CPM authority | PASS | 1.4335 | frontend-components.json
UI-1 | CWA_CONTAINER_CREATED | PASS |  | chromium/browser-uat.json

## 03_Work_Packages
Paquetes y ciclo de vida
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_tailored_types_are_ready_without_auto_release[EWP] | PASS | 0.006 | postgres-junit.xml
TC-2 | test_tailored_types_are_ready_without_auto_release[PWP] | PASS | 0.004 | postgres-junit.xml
TC-3 | test_tailored_types_are_ready_without_auto_release[CWP] | PASS | 0.005 | postgres-junit.xml
TC-4 | test_tailored_types_are_ready_without_auto_release[IWP] | PASS | 0.004 | postgres-junit.xml
TC-5 | test_tailored_types_are_ready_without_auto_release[TWP] | PASS | 0.004 | postgres-junit.xml
TC-6 | test_tailored_types_are_ready_without_auto_release[SUPPORT] | PASS | 0.004 | postgres-junit.xml
TC-7 | test_tailored_types_are_ready_without_auto_release[LOGISTICS] | PASS | 0.005 | postgres-junit.xml
TC-8 | test_tailored_types_are_ready_without_auto_release[TEMPORARY_WORKS] | PASS | 0.006 | postgres-junit.xml
TC-9 | test_cycle_detection_not_a_false_package_type_hierarchy[edges0-False] | PASS | 0.01 | postgres-junit.xml
TC-10 | test_cycle_detection_not_a_false_package_type_hierarchy[edges1-True] | PASS | 0.006 | postgres-junit.xml
TC-11 | test_cycle_detection_not_a_false_package_type_hierarchy[edges2-True] | PASS | 0.004 | postgres-junit.xml
TC-12 | test_cycle_detection_not_a_false_package_type_hierarchy[edges3-False] | PASS | 0.005 | postgres-junit.xml
TC-13 | test_commands_cannot_smuggle_cpm_mutations[PackageIn-body0] | PASS | 0.008 | postgres-junit.xml
TC-14 | test_governed_package_types_without_dates[EWP] | PASS | 0.883 | postgres-junit.xml
TC-15 | test_governed_package_types_without_dates[PWP] | PASS | 0.81 | postgres-junit.xml
TC-16 | test_governed_package_types_without_dates[CWP] | PASS | 0.767 | postgres-junit.xml
TC-17 | test_governed_package_types_without_dates[IWP] | PASS | 0.428 | postgres-junit.xml
TC-18 | test_governed_package_types_without_dates[TWP] | PASS | 0.461 | postgres-junit.xml
TC-19 | test_governed_package_types_without_dates[SUPPORT] | PASS | 0.306 | postgres-junit.xml
TC-20 | test_governed_package_types_without_dates[LOGISTICS] | PASS | 1.147 | postgres-junit.xml
TC-21 | test_governed_package_types_without_dates[TEMPORARY_WORKS] | PASS | 0.554 | postgres-junit.xml
TC-22 | test_governed_constraint_types_preserve_due_date_no_auto_clear[ENGINEERING] | PASS | 0.292 | postgres-junit.xml
TC-23 | test_governed_constraint_types_preserve_due_date_no_auto_clear[PROCUREMENT] | PASS | 0.255 | postgres-junit.xml
TC-24 | test_governed_constraint_types_preserve_due_date_no_auto_clear[MATERIAL] | PASS | 0.289 | postgres-junit.xml
TC-25 | test_governed_constraint_types_preserve_due_date_no_auto_clear[LOGISTICS] | PASS | 0.222 | postgres-junit.xml
TC-26 | test_governed_constraint_types_preserve_due_date_no_auto_clear[ACCESS] | PASS | 0.267 | postgres-junit.xml
TC-27 | test_governed_constraint_types_preserve_due_date_no_auto_clear[WORKFRONT] | PASS | 0.331 | postgres-junit.xml
TC-28 | test_governed_constraint_types_preserve_due_date_no_auto_clear[PREDECESSOR] | PASS | 1.099 | postgres-junit.xml
TC-29 | test_governed_constraint_types_preserve_due_date_no_auto_clear[PERMIT] | PASS | 0.955 | postgres-junit.xml
TC-30 | test_governed_constraint_types_preserve_due_date_no_auto_clear[QUALITY] | PASS | 1.028 | postgres-junit.xml
TC-31 | test_governed_constraint_types_preserve_due_date_no_auto_clear[HSE] | PASS | 0.318 | postgres-junit.xml
TC-32 | test_governed_constraint_types_preserve_due_date_no_auto_clear[RESOURCE] | PASS | 0.294 | postgres-junit.xml
TC-33 | test_governed_constraint_types_preserve_due_date_no_auto_clear[EQUIPMENT] | PASS | 0.261 | postgres-junit.xml
TC-34 | test_governed_constraint_types_preserve_due_date_no_auto_clear[TEMPORARY_WORKS] | PASS | 0.261 | postgres-junit.xml
TC-35 | test_governed_constraint_types_preserve_due_date_no_auto_clear[INTERFACE] | PASS | 0.344 | postgres-junit.xml
TC-36 | test_governed_constraint_types_preserve_due_date_no_auto_clear[CLIENT_DECISION] | PASS | 0.262 | postgres-junit.xml
TC-37 | test_governed_constraint_types_preserve_due_date_no_auto_clear[CONTRACTUAL] | PASS | 0.282 | postgres-junit.xml
TC-38 | test_governed_constraint_types_preserve_due_date_no_auto_clear[OTHER] | PASS | 0.284 | postgres-junit.xml
TC-39 | test_package_idempotency_rbac_tenant_project_and_missing_ifmatch | PASS | 0.978 | postgres-junit.xml
TC-40 | test_package_scope_plan_activity_many_to_many_without_source_mutation | PASS | 12.132 | postgres-junit.xml
TC-41 | test_blocking_clear_evidence_readiness_independent_release_and_history | PASS | 14.631 | postgres-junit.xml
TC-42 | test_postgres_history_immutable[awp_package_mappings] | PASS | 0.029 | postgres-junit.xml
TC-43 | test_package_manager_authority_cannot_bypass_release_sod[preparer] | PASS | 8.775 | postgres-junit.xml
TC-44 | test_package_manager_authority_cannot_bypass_release_sod[assessor] | PASS | 5.501 | postgres-junit.xml
TC-45 | test_complete_closed_package_does_not_clear_execution_condition | PASS | 8.387 | postgres-junit.xml
TC-46 | test_all_required_filter_dimensions_real_source[package_type] | PASS | 0.827 | postgres-junit.xml
TC-47 | test_all_required_filter_dimensions_real_source[work_package_id] | PASS | 0.697 | postgres-junit.xml
TC-48 | test_partial_current_package_membership_fails_closed_without_rewriting_schedule | PASS | 1.915 | postgres-junit.xml
TC-49 | test_four_relationship_types_signed_lags_and_external_identity_preserved[xml] | PASS | 0.012 | regression-junit.xml
TC-50 | test_four_relationship_types_signed_lags_and_external_identity_preserved[xer] | PASS | 0.009 | regression-junit.xml
TC-51 | test_xml_constraints_primary_and_secondary_preserve_types_and_dates | PASS | 0.018 | regression-junit.xml
TC-52 | AWP canonical project presentation has separate CWA/packages/execution constraint/readiness navigation and no CPM authority | PASS | 1.4335 | frontend-components.json
TC-53 | AWP canonical project presentation shows configured package extensions rather than a second hardcoded catalog | PASS | 0.27933 | frontend-components.json
TC-54 | AWP canonical project presentation maps published Plan to existing Package with its own ETag and explicit phase | PASS | 0.63522 | frontend-components.json
TC-55 | AWP canonical project presentation submits explicit as-of and evidence separately from independent release | PASS | 0.29459 | frontend-components.json
TC-56 | AWP canonical project presentation does not permit release when readiness source hashes are stale | PASS | 0.12217 | frontend-components.json
TC-57 | O1B-B frontend contracts — component tests are not real-browser release evidence uses canonical Schedule Workspace routes without legacy Project fallback | PASS | 0.10738 | frontend-components.json
TC-58 | O1B-B frontend contracts — component tests are not real-browser release evidence uses If-Match and idempotency on material commands | PASS | 0.0098551 | frontend-components.json
TC-59 | O1B-B frontend contracts — component tests are not real-browser release evidence uploads a genuine file to register staging with expected register version | PASS | 0.011692 | frontend-components.json
TC-60 | O1B-B frontend contracts — component tests are not real-browser release evidence shows coherent read-only submodules and no writer controls | PASS | 1.5185 | frontend-components.json
TC-61 | O1B-B frontend contracts — component tests are not real-browser release evidence creates a Schedule Register without guessing hours per day | PASS | 0.45901 | frontend-components.json
TC-62 | O1B-B frontend contracts — component tests are not real-browser release evidence creates a successor snapshot instead of editing existing WBS or approved data in place | PASS | 0.35225 | frontend-components.json
TC-63 | O1B-B frontend contracts — component tests are not real-browser release evidence keeps WBS hierarchy separate from Scope hierarchy and handles orphan source parents | PASS | 0.068927 | frontend-components.json
TC-64 | O1B-B frontend contracts — component tests are not real-browser release evidence maps multiple Plan Items to an Activity with explicit reason and version | PASS | 0.15877 | frontend-components.json
TC-65 | O1B-B frontend contracts — component tests are not real-browser release evidence maps WBS to approved Scope without silently creating Scope | PASS | 0.17423 | frontend-components.json
TC-66 | O1B-B frontend contracts — component tests are not real-browser release evidence does not offer editing mappings of an accepted immutable version | PASS | 0.05263 | frontend-components.json
TC-67 | O1B-B frontend contracts — component tests are not real-browser release evidence does not offer Draft Plan Items or Scope outside the approved current baseline | PASS | 0.054422 | frontend-components.json
TC-68 | O1B-B frontend contracts — component tests are not real-browser release evidence respects a profile disabling direct Scope mappings | PASS | 0.091902 | frontend-components.json
TC-69 | O1B-B frontend contracts — component tests are not real-browser release evidence loads existing mappings for explicit re-review and retains removal as an audit command | PASS | 0.14467 | frontend-components.json
TC-70 | O1B-B frontend contracts — component tests are not real-browser release evidence preserves missing float as UNKNOWN and actual zero or false as source values | PASS | 0.30765 | frontend-components.json
TC-71 | O1B-B frontend contracts — component tests are not real-browser release evidence preserves ten-hour calendar exceptions without an eight-hour conversion | PASS | 0.12712 | frontend-components.json
TC-72 | O1B-B frontend contracts — component tests are not real-browser release evidence shows SF and negative lag with external unresolved references | PASS | 0.11355 | frontend-components.json
TC-73 | O1B-B frontend contracts — component tests are not real-browser release evidence keeps Activity Codes and constraints as distinct source collections | PASS | 0.14583 | frontend-components.json
TC-74 | O1B-B frontend contracts — component tests are not real-browser release evidence stages native P6 file without auto-accepting Current or Baseline | PASS | 0.10633 | frontend-components.json
TC-75 | O1B-B frontend contracts — component tests are not real-browser release evidence accepts Current only through the explicit reviewed-version command | PASS | 0.037882 | frontend-components.json
TC-76 | O1B-B frontend contracts — component tests are not real-browser release evidence generates only the supported XML export manifest rather than fake CSV roundtrip | PASS | 0.043688 | frontend-components.json
TC-77 | O1B-B frontend contracts — component tests are not real-browser release evidence uses governed baseline lifecycle independent from accepted Current | PASS | 0.053787 | frontend-components.json
TC-78 | O1B-B frontend contracts — component tests are not real-browser release evidence does not expose mutation controls on an approved Baseline | PASS | 0.05214 | frontend-components.json
TC-79 | O1B-B frontend contracts — component tests are not real-browser release evidence associates period explicitly without forcing Data Date to cutoff | PASS | 0.097102 | frontend-components.json
TC-80 | O1B-B frontend contracts — component tests are not real-browser release evidence renders safely before a Schedule Profile has been bound | PASS | 0.20872 | frontend-components.json
TC-81 | O1B-B frontend contracts — component tests are not real-browser release evidence gets float classification from a read-only server query without local CPM calculation | PASS | 0.060219 | frontend-components.json
TC-82 | O1B-B frontend contracts — component tests are not real-browser release evidence refreshes health through a read-only query rather than mutating validation evidence | PASS | 0.024328 | frontend-components.json
TC-83 | O1B-B frontend contracts — component tests are not real-browser release evidence requires an explicit approved previous baseline when preparing a rebaseline | PASS | 0.096031 | frontend-components.json
TC-84 | O1B-B frontend contracts — component tests are not real-browser release evidence uses native manifest fields and downloads the actual source file name | PASS | 0.046184 | frontend-components.json
TC-85 | O1B-B frontend contracts — component tests are not real-browser release evidence does not allow revalidation after independent review has begun | PASS | 0.036491 | frontend-components.json
TC-86 | O1B-B frontend contracts — component tests are not real-browser release evidence queries canonical activity classification and health without command headers | PASS | 0.0043285 | frontend-components.json
TC-87 | O1B-B frontend contracts — component tests are not real-browser release evidence ADMIN creates Schedule Profile through its dedicated guarded API | PASS | 0.15453 | frontend-components.json
TC-88 | 4D source fidelity and display uses server filters for Package, WBS, Scope and Plan and exposes 16 filters | PASS | 0.75899 | frontend-components.json
UI-1 | ALL_FIVE_BASE_TYPES_SUPPORT_LOGISTICS_AND_PHASED_MN_MAPPINGS | PASS |  | chromium/browser-uat.json
UI-2 | CLEARED_READY_NOT_AUTORELEASED | PASS |  | chromium/browser-uat.json
UI-3 | INDEPENDENT_EXPLICIT_PACKAGE_RELEASE | PASS |  | chromium/browser-uat.json
UI-4 | FOUR_D_FILTER_AND_IFC_SCOPE_PLAN_PACKAGE_ACTIVITY_TRACEABILITY | PASS |  | chromium/browser-uat.json
UI-5 | FOUR_D_BROWSER_FILTER_PACKAGE | PASS |  | chromium/browser-uat.json

## 04_Package_Mappings
Mapeos Scope Plan Package Activity
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_no_scope_mapping_blocks_and_profile_can_require_activity | PASS | 0.005 | postgres-junit.xml
TC-2 | test_commands_cannot_smuggle_cpm_mutations[MappingIn-body2] | PASS | 0.006 | postgres-junit.xml
TC-3 | test_package_scope_plan_activity_many_to_many_without_source_mutation | PASS | 12.132 | postgres-junit.xml
TC-4 | test_nonblocking_waiver_and_constraint_all_level_mappings | PASS | 7.202 | postgres-junit.xml
TC-5 | test_postgres_history_immutable[awp_package_mappings] | PASS | 0.029 | postgres-junit.xml
TC-6 | test_postgres_history_immutable[awp_constraint_mappings] | PASS | 0.035 | postgres-junit.xml
TC-7 | test_postgres_mapping_rejects_cross_tenant_and_project_references | PASS | 0.444 | postgres-junit.xml
TC-8 | test_missing_broken_date_or_phase_is_not_healthy_completion[activities0-ACTIVITY_MAPPING_REQUIRED] | PASS | 0.005 | postgres-junit.xml
TC-9 | test_profile_invalid_authority_flags_rejected[mapping_completeness_policy-IGNORE] | PASS | 0.006 | postgres-junit.xml
TC-10 | test_profile_invalid_authority_flags_rejected[allow_direct_scope_mapping-yes] | PASS | 0.011 | postgres-junit.xml
TC-11 | test_wbs_plan_and_activity_plan_many_to_many_and_baseline_current_separation | PASS | 11.104 | regression-junit.xml
TC-12 | test_acceptance_rejects_last_material_mapping_editor_and_importer | PASS | 4.106 | regression-junit.xml
TC-13 | test_mapping_wrong_tenant_project_and_unknown_external_identity_denied | PASS | 1.681 | regression-junit.xml
TC-14 | test_accepted_schedule_mapping_and_source_snapshot_immutable | PASS | 4.483 | regression-junit.xml
TC-15 | test_broken_identity_mapping_retained_and_blocks_successor | PASS | 4.583 | regression-junit.xml
TC-16 | test_mandatory_wbs_mappings_are_distinct_from_activity_mappings | PASS | 1.316 | regression-junit.xml
TC-17 | test_invalid_authority_or_policy_is_rejected_before_persistence[mapping_policy-value6] | PASS | 0.159 | regression-junit.xml
TC-18 | test_identity_based_diff_preserves_mapping_impacts_and_source_immutability | PASS | 0.017 | regression-junit.xml
TC-19 | test_ifc_version_diff_stable_guid_and_mapping_loss | PASS | 0.215 | regression-junit.xml
TC-20 | test_excel_invalid_headers_mapping_and_duplicate_header | PASS | 0.011 | regression-junit.xml
TC-21 | test_excel_field_mapping_existing_parent_future_apu_mapping_stays_inactive | PASS | 0.009 | regression-junit.xml
TC-22 | test_real_ifc_version_acceptance_source_bytes_and_mn_scope_mapping | PASS | 4.661 | regression-junit.xml
TC-23 | test_plan_many_to_many_group_split_recompose_and_derived_lineage | PASS | 8.065 | regression-junit.xml
TC-24 | O1B-B frontend contracts — component tests are not real-browser release evidence does not offer editing mappings of an accepted immutable version | PASS | 0.05263 | frontend-components.json
TC-25 | O1B-B frontend contracts — component tests are not real-browser release evidence respects a profile disabling direct Scope mappings | PASS | 0.091902 | frontend-components.json
TC-26 | O1B-B frontend contracts — component tests are not real-browser release evidence loads existing mappings for explicit re-review and retains removal as an audit command | PASS | 0.14467 | frontend-components.json
UI-1 | ALL_FIVE_BASE_TYPES_SUPPORT_LOGISTICS_AND_PHASED_MN_MAPPINGS | PASS |  | chromium/browser-uat.json

## 05_Package_Dependencies
Dependencias de ejecución
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_dependency_is_execution_not_cpm | PASS | 0.005 | postgres-junit.xml
TC-2 | test_cycle_detection_not_a_false_package_type_hierarchy[edges0-False] | PASS | 0.01 | postgres-junit.xml
TC-3 | test_cycle_detection_not_a_false_package_type_hierarchy[edges1-True] | PASS | 0.006 | postgres-junit.xml
TC-4 | test_cycle_detection_not_a_false_package_type_hierarchy[edges2-True] | PASS | 0.004 | postgres-junit.xml
TC-5 | test_cycle_detection_not_a_false_package_type_hierarchy[edges3-False] | PASS | 0.005 | postgres-junit.xml
TC-6 | test_large_dependency_graph_has_no_recursive_stack_limit | PASS | 0.032 | postgres-junit.xml
TC-7 | test_cwa_container_hierarchy_and_cycle_etag | PASS | 36.132 | postgres-junit.xml
TC-8 | test_dependency_graph_no_false_type_chain_cycle_and_history | PASS | 3.482 | postgres-junit.xml
TC-9 | test_structural_and_source_validation_failure_cases[wbs_cycle-<lambda>-WBS_HIERARCHY_CYCLE] | PASS | 0.015 | regression-junit.xml
TC-10 | test_excel_duplicate_scope_code_source_row_and_cycle_detection | PASS | 0.015 | regression-junit.xml
TC-11 | O1B-B frontend contracts — component tests are not real-browser release evidence uses governed baseline lifecycle independent from accepted Current | PASS | 0.053787 | frontend-components.json

## 06_Execution_Constraints
Restricciones de ejecución
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_due_date_never_clears_blocker[OPEN] | PASS | 0.005 | postgres-junit.xml
TC-2 | test_due_date_never_clears_blocker[IN_PROGRESS] | PASS | 0.005 | postgres-junit.xml
TC-3 | test_resolved_constraint_no_longer_blocks[CLEARED] | PASS | 0.005 | postgres-junit.xml
TC-4 | test_resolved_constraint_no_longer_blocks[WAIVED] | PASS | 0.004 | postgres-junit.xml
TC-5 | test_resolved_constraint_no_longer_blocks[CANCELLED] | PASS | 0.005 | postgres-junit.xml
TC-6 | test_commands_cannot_smuggle_cpm_mutations[ConstraintIn-body1] | PASS | 0.003 | postgres-junit.xml
TC-7 | test_governed_constraint_types_preserve_due_date_no_auto_clear[ENGINEERING] | PASS | 0.292 | postgres-junit.xml
TC-8 | test_governed_constraint_types_preserve_due_date_no_auto_clear[PROCUREMENT] | PASS | 0.255 | postgres-junit.xml
TC-9 | test_governed_constraint_types_preserve_due_date_no_auto_clear[MATERIAL] | PASS | 0.289 | postgres-junit.xml
TC-10 | test_governed_constraint_types_preserve_due_date_no_auto_clear[LOGISTICS] | PASS | 0.222 | postgres-junit.xml
TC-11 | test_governed_constraint_types_preserve_due_date_no_auto_clear[ACCESS] | PASS | 0.267 | postgres-junit.xml
TC-12 | test_governed_constraint_types_preserve_due_date_no_auto_clear[WORKFRONT] | PASS | 0.331 | postgres-junit.xml
TC-13 | test_governed_constraint_types_preserve_due_date_no_auto_clear[PREDECESSOR] | PASS | 1.099 | postgres-junit.xml
TC-14 | test_governed_constraint_types_preserve_due_date_no_auto_clear[PERMIT] | PASS | 0.955 | postgres-junit.xml
TC-15 | test_governed_constraint_types_preserve_due_date_no_auto_clear[QUALITY] | PASS | 1.028 | postgres-junit.xml
TC-16 | test_governed_constraint_types_preserve_due_date_no_auto_clear[HSE] | PASS | 0.318 | postgres-junit.xml
TC-17 | test_governed_constraint_types_preserve_due_date_no_auto_clear[RESOURCE] | PASS | 0.294 | postgres-junit.xml
TC-18 | test_governed_constraint_types_preserve_due_date_no_auto_clear[EQUIPMENT] | PASS | 0.261 | postgres-junit.xml
TC-19 | test_governed_constraint_types_preserve_due_date_no_auto_clear[TEMPORARY_WORKS] | PASS | 0.261 | postgres-junit.xml
TC-20 | test_governed_constraint_types_preserve_due_date_no_auto_clear[INTERFACE] | PASS | 0.344 | postgres-junit.xml
TC-21 | test_governed_constraint_types_preserve_due_date_no_auto_clear[CLIENT_DECISION] | PASS | 0.262 | postgres-junit.xml
TC-22 | test_governed_constraint_types_preserve_due_date_no_auto_clear[CONTRACTUAL] | PASS | 0.282 | postgres-junit.xml
TC-23 | test_governed_constraint_types_preserve_due_date_no_auto_clear[OTHER] | PASS | 0.284 | postgres-junit.xml
TC-24 | test_blocking_clear_evidence_readiness_independent_release_and_history | PASS | 14.631 | postgres-junit.xml
TC-25 | test_nonblocking_waiver_and_constraint_all_level_mappings | PASS | 7.202 | postgres-junit.xml
TC-26 | test_postgres_history_immutable[awp_constraint_mappings] | PASS | 0.035 | postgres-junit.xml
TC-27 | test_complete_closed_package_does_not_clear_execution_condition | PASS | 8.387 | postgres-junit.xml
TC-28 | test_readiness_blocker_is_separate_from_imported_scheduled_state | PASS | 1.061 | postgres-junit.xml
TC-29 | test_published_health_policy_checks_without_cpm[hard_constraint-SCHEDULE_HARD_CONSTRAINT-True] | PASS | 4.78 | regression-junit.xml
TC-30 | test_invalid_authority_or_policy_is_rejected_before_persistence[allowed_constraints-value7] | PASS | 0.143 | regression-junit.xml
TC-31 | test_xml_constraints_primary_and_secondary_preserve_types_and_dates | PASS | 0.018 | regression-junit.xml
TC-32 | test_untrusted_draft_identity_labels_and_metadata_return_validation_not_500[constraints-activity_external_id-value6] | PASS | 0.009 | regression-junit.xml
TC-33 | AWP canonical project presentation has separate CWA/packages/execution constraint/readiness navigation and no CPM authority | PASS | 1.4335 | frontend-components.json
TC-34 | AWP canonical project presentation clears only by explicit command containing evidence and version | PASS | 0.3411 | frontend-components.json
TC-35 | O1B-B frontend contracts — component tests are not real-browser release evidence keeps Activity Codes and constraints as distinct source collections | PASS | 0.14583 | frontend-components.json
UI-1 | SCHEDULED_NOT_READY_BLOCKER | PASS |  | chromium/browser-uat.json
UI-2 | CLEARED_READY_NOT_AUTORELEASED | PASS |  | chromium/browser-uat.json

## 07_Readiness
Evaluación y preparación del frente
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_tailored_types_are_ready_without_auto_release[EWP] | PASS | 0.006 | postgres-junit.xml
TC-2 | test_tailored_types_are_ready_without_auto_release[PWP] | PASS | 0.004 | postgres-junit.xml
TC-3 | test_tailored_types_are_ready_without_auto_release[CWP] | PASS | 0.005 | postgres-junit.xml
TC-4 | test_tailored_types_are_ready_without_auto_release[IWP] | PASS | 0.004 | postgres-junit.xml
TC-5 | test_tailored_types_are_ready_without_auto_release[TWP] | PASS | 0.004 | postgres-junit.xml
TC-6 | test_tailored_types_are_ready_without_auto_release[SUPPORT] | PASS | 0.004 | postgres-junit.xml
TC-7 | test_tailored_types_are_ready_without_auto_release[LOGISTICS] | PASS | 0.005 | postgres-junit.xml
TC-8 | test_tailored_types_are_ready_without_auto_release[TEMPORARY_WORKS] | PASS | 0.006 | postgres-junit.xml
TC-9 | test_missing_mandatory_evidence_is_not_ready | PASS | 0.005 | postgres-junit.xml
TC-10 | test_blocking_clear_evidence_readiness_independent_release_and_history | PASS | 14.631 | postgres-junit.xml
TC-11 | test_postgres_history_immutable[awp_readiness_assessments] | PASS | 0.021 | postgres-junit.xml
TC-12 | test_package_manager_authority_cannot_bypass_release_sod[preparer] | PASS | 8.775 | postgres-junit.xml
TC-13 | test_package_manager_authority_cannot_bypass_release_sod[assessor] | PASS | 5.501 | postgres-junit.xml
TC-14 | test_scheduled_readiness_overlay_does_not_modify_schedule_state_or_logic | PASS | 0.003 | postgres-junit.xml
TC-15 | test_all_required_filter_dimensions_real_source[execution_readiness] | PASS | 0.724 | postgres-junit.xml
TC-16 | test_readiness_blocker_is_separate_from_imported_scheduled_state | PASS | 1.061 | postgres-junit.xml
TC-17 | AWP canonical project presentation has separate CWA/packages/execution constraint/readiness navigation and no CPM authority | PASS | 1.4335 | frontend-components.json
TC-18 | AWP canonical project presentation does not permit release when readiness source hashes are stale | PASS | 0.12217 | frontend-components.json
UI-1 | SCHEDULED_NOT_READY_BLOCKER | PASS |  | chromium/browser-uat.json
UI-2 | CLEARED_READY_NOT_AUTORELEASED | PASS |  | chromium/browser-uat.json
UI-3 | FOUR_D_ORIGINAL_IFC_REAL_GEOMETRY_ALL_NATURES_READINESS_OVERLAY | PASS |  | chromium/browser-uat.json

## 08_Schedule_Integration
Integración sin mutación de Schedule
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_package_scope_plan_activity_many_to_many_without_source_mutation | PASS | 12.132 | postgres-junit.xml
TC-2 | test_actual_dates_current_and_planned_baseline_are_distinct_sources | PASS | 0.003 | postgres-junit.xml
TC-3 | test_scheduled_readiness_overlay_does_not_modify_schedule_state_or_logic | PASS | 0.003 | postgres-junit.xml
TC-4 | test_semantic_comparison_no_forecast_cpm[2026-10-24-2026-10-20-BEHIND_BASELINE] | PASS | 0.006 | postgres-junit.xml
TC-5 | test_semantic_comparison_no_forecast_cpm[2026-10-20-2026-10-24-AHEAD_OF_BASELINE] | PASS | 0.008 | postgres-junit.xml
TC-6 | test_explicit_control_period_association_does_not_substitute_cutoff_for_data_date | PASS | 3.432 | postgres-junit.xml
TC-7 | test_approved_baseline_reuses_frozen_snapshot_even_version_superseded | PASS | 1.457 | postgres-junit.xml
TC-8 | test_baseline_current_same_date_comparison_exposes_variance_no_cpm | PASS | 2.778 | postgres-junit.xml
TC-9 | test_readiness_blocker_is_separate_from_imported_scheduled_state | PASS | 1.061 | postgres-junit.xml
TC-10 | test_partial_current_package_membership_fails_closed_without_rewriting_schedule | PASS | 1.915 | postgres-junit.xml
TC-11 | test_awp_additive_upgrade_downgrade_reupgrade_preserves_schedule_structure | PASS | 13.382 | postgres-junit.xml
TC-12 | test_schedule_register_write_duties_and_project_assignment[executive] | PASS | 0.079 | regression-junit.xml
TC-13 | test_schedule_register_write_duties_and_project_assignment[scope_manager] | PASS | 0.09 | regression-junit.xml
TC-14 | test_schedule_register_write_duties_and_project_assignment[bim_manager] | PASS | 0.049 | regression-junit.xml
TC-15 | test_schedule_register_write_duties_and_project_assignment[construction_manager] | PASS | 0.05 | regression-junit.xml
TC-16 | test_schedule_register_write_duties_and_project_assignment[cost_controller] | PASS | 0.046 | regression-junit.xml
TC-17 | test_schedule_register_write_duties_and_project_assignment[unassigned] | PASS | 0.059 | regression-junit.xml
TC-18 | test_schedule_register_write_duties_and_project_assignment[foreign] | PASS | 0.059 | regression-junit.xml
TC-19 | test_schedule_granular_read_roles_reuse_current_operational_context[manager] | PASS | 0.8 | regression-junit.xml
TC-20 | test_schedule_granular_read_roles_reuse_current_operational_context[second_manager] | PASS | 0.776 | regression-junit.xml
TC-21 | test_schedule_granular_read_roles_reuse_current_operational_context[planner] | PASS | 0.764 | regression-junit.xml
TC-22 | test_schedule_granular_read_roles_reuse_current_operational_context[scope_manager] | PASS | 0.689 | regression-junit.xml
TC-23 | test_schedule_granular_read_roles_reuse_current_operational_context[bim_manager] | PASS | 0.79 | regression-junit.xml
TC-24 | test_schedule_granular_read_roles_reuse_current_operational_context[construction_manager] | PASS | 0.866 | regression-junit.xml
TC-25 | test_schedule_granular_read_roles_reuse_current_operational_context[cost_controller] | PASS | 0.747 | regression-junit.xml
TC-26 | test_schedule_granular_read_roles_reuse_current_operational_context[executive] | PASS | 0.666 | regression-junit.xml
TC-27 | test_unmapped_schedule_cannot_accept_or_approve_baseline | PASS | 1.024 | regression-junit.xml
TC-28 | test_wbs_plan_and_activity_plan_many_to_many_and_baseline_current_separation | PASS | 11.104 | regression-junit.xml
TC-29 | test_accepted_schedule_mapping_and_source_snapshot_immutable | PASS | 4.483 | regression-junit.xml
TC-30 | test_get_schedule_overview_and_profiles_have_no_sql_writes | PASS | 2.79 | regression-junit.xml
TC-31 | test_explicit_period_association_preserves_data_date_distinct_from_cutoff | PASS | 4.664 | regression-junit.xml
TC-32 | test_baseline_sod_and_database_immutability | PASS | 6.833 | regression-junit.xml
TC-33 | test_published_health_policy_checks_without_cpm[negative_lag-SCHEDULE_NEGATIVE_LAG-True] | PASS | 4.063 | regression-junit.xml
TC-34 | test_published_health_policy_checks_without_cpm[hard_constraint-SCHEDULE_HARD_CONSTRAINT-True] | PASS | 4.78 | regression-junit.xml
TC-35 | test_published_health_policy_checks_without_cpm[open_ends-SCHEDULE_OPEN_ENDS-True] | PASS | 6.23 | regression-junit.xml
TC-36 | test_published_health_policy_checks_without_cpm[missing_calendar-SCHEDULE_CALENDAR_REFERENCE_MISSING-True] | PASS | 5.058 | regression-junit.xml
TC-37 | test_published_health_policy_checks_without_cpm[long_duration-SCHEDULE_LONG_DURATION-False] | PASS | 5.331 | regression-junit.xml
TC-38 | test_published_health_policy_checks_without_cpm[excessive_lag-SCHEDULE_EXCESSIVE_LAG-False] | PASS | 5.423 | regression-junit.xml
TC-39 | test_legacy_admin_cannot_bypass_governed_schedule_profile[create] | PASS | 0.07 | regression-junit.xml
TC-40 | test_legacy_admin_cannot_bypass_governed_schedule_profile[patch] | PASS | 0.053 | regression-junit.xml
TC-41 | test_legacy_admin_cannot_bypass_governed_schedule_profile[publish] | PASS | 0.044 | regression-junit.xml
TC-42 | test_legacy_admin_cannot_bypass_governed_schedule_profile[clone] | PASS | 0.044 | regression-junit.xml
TC-43 | test_two_successor_baselines_same_source_cannot_approve_stale_predecessor | PASS | 13.312 | regression-junit.xml
TC-44 | test_schedule_commands_do_not_create_scope_plan_or_derived_authorities | PASS | 7.241 | regression-junit.xml
TC-45 | test_real_schedule_source_data_date_wbs_activities_calendars_and_hash[xml] | PASS | 0.011 | regression-junit.xml
TC-46 | test_real_schedule_source_data_date_wbs_activities_calendars_and_hash[xer] | PASS | 0.014 | regression-junit.xml
TC-47 | test_xml_export_is_actual_xml_parser_loop_with_core_semantics_and_no_native_baseline_claim | PASS | 0.031 | regression-junit.xml
TC-48 | test_excel_invalid_governed_values_block_candidate[Scope Type-COST_BASELINE-INVALID_SCOPE_TYPE] | PASS | 0.008 | regression-junit.xml
TC-49 | test_scope_hierarchy_draft_etag_and_immutable_baseline_successor | PASS | 7.304 | regression-junit.xml
TC-50 | test_postgresql_baseline_raw_update_rejected | PASS | 4.27 | regression-junit.xml
TC-51 | application navigation composition keeps the Schedule canonical workspace boundary explicit without deleting legacy schedule adapters | PASS | 0.017793 | frontend-components.json
TC-52 | O1B-B frontend contracts — component tests are not real-browser release evidence uses canonical Schedule Workspace routes without legacy Project fallback | PASS | 0.10738 | frontend-components.json
TC-53 | O1B-B frontend contracts — component tests are not real-browser release evidence creates a Schedule Register without guessing hours per day | PASS | 0.45901 | frontend-components.json
TC-54 | O1B-B frontend contracts — component tests are not real-browser release evidence does not offer Draft Plan Items or Scope outside the approved current baseline | PASS | 0.054422 | frontend-components.json
TC-55 | O1B-B frontend contracts — component tests are not real-browser release evidence stages native P6 file without auto-accepting Current or Baseline | PASS | 0.10633 | frontend-components.json
TC-56 | O1B-B frontend contracts — component tests are not real-browser release evidence uses governed baseline lifecycle independent from accepted Current | PASS | 0.053787 | frontend-components.json
TC-57 | O1B-B frontend contracts — component tests are not real-browser release evidence does not expose mutation controls on an approved Baseline | PASS | 0.05214 | frontend-components.json
TC-58 | O1B-B frontend contracts — component tests are not real-browser release evidence associates period explicitly without forcing Data Date to cutoff | PASS | 0.097102 | frontend-components.json
TC-59 | O1B-B frontend contracts — component tests are not real-browser release evidence renders safely before a Schedule Profile has been bound | PASS | 0.20872 | frontend-components.json
TC-60 | O1B-B frontend contracts — component tests are not real-browser release evidence requires an explicit approved previous baseline when preparing a rebaseline | PASS | 0.096031 | frontend-components.json
TC-61 | O1B-B frontend contracts — component tests are not real-browser release evidence ADMIN creates Schedule Profile through its dedicated guarded API | PASS | 0.15453 | frontend-components.json
TC-62 | 4D source fidelity and display lists only accepted current and approved baselines, using actual Data Date | PASS | 2.1851 | frontend-components.json
TC-63 | 4D source fidelity and display compares baseline/current on the same selected date without a write command | PASS | 0.50238 | frontend-components.json
UI-1 | SCHEDULED_NOT_READY_BLOCKER | PASS |  | chromium/browser-uat.json
UI-2 | BASELINE_CURRENT_COMPARISON_EXPLICIT_DATA_DATE | PASS |  | chromium/browser-uat.json

## 09_4D_Mappings
Fuentes y mapeos 4D
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_governed_constraint_types_preserve_due_date_no_auto_clear[RESOURCE] | PASS | 0.294 | postgres-junit.xml
TC-2 | test_package_scope_plan_activity_many_to_many_without_source_mutation | PASS | 12.132 | postgres-junit.xml
TC-3 | test_actual_dates_current_and_planned_baseline_are_distinct_sources | PASS | 0.003 | postgres-junit.xml
TC-4 | test_comparison_unresolved_or_missing_source_explicit | PASS | 0.003 | postgres-junit.xml
TC-5 | test_filter_contract_supports_every_required_dimension_without_mutation | PASS | 0.004 | postgres-junit.xml
TC-6 | test_wbs_filter_membership_includes_source_ancestors_without_tree_rewrite | PASS | 0.003 | postgres-junit.xml
TC-7 | test_current_source_explicit_data_date_and_governed_sources_only | PASS | 56.328 | postgres-junit.xml
TC-8 | test_all_required_filter_dimensions_real_source[wbs] | PASS | 0.781 | postgres-junit.xml
TC-9 | test_all_required_filter_dimensions_real_source[activity] | PASS | 0.765 | postgres-junit.xml
TC-10 | test_all_required_filter_dimensions_real_source[scope_item_id] | PASS | 0.718 | postgres-junit.xml
TC-11 | test_all_required_filter_dimensions_real_source[scope_nature] | PASS | 0.957 | postgres-junit.xml
TC-12 | test_all_required_filter_dimensions_real_source[plan_item_id] | PASS | 0.932 | postgres-junit.xml
TC-13 | test_all_required_filter_dimensions_real_source[cwa_id] | PASS | 1.215 | postgres-junit.xml
TC-14 | test_all_required_filter_dimensions_real_source[package_type] | PASS | 0.827 | postgres-junit.xml
TC-15 | test_all_required_filter_dimensions_real_source[work_package_id] | PASS | 0.697 | postgres-junit.xml
TC-16 | test_all_required_filter_dimensions_real_source[area] | PASS | 0.746 | postgres-junit.xml
TC-17 | test_all_required_filter_dimensions_real_source[zone] | PASS | 0.803 | postgres-junit.xml
TC-18 | test_all_required_filter_dimensions_real_source[system] | PASS | 1.019 | postgres-junit.xml
TC-19 | test_all_required_filter_dimensions_real_source[activity_status] | PASS | 0.973 | postgres-junit.xml
TC-20 | test_all_required_filter_dimensions_real_source[critical] | PASS | 0.67 | postgres-junit.xml
TC-21 | test_all_required_filter_dimensions_real_source[near_critical] | PASS | 0.608 | postgres-junit.xml
TC-22 | test_all_required_filter_dimensions_real_source[execution_readiness] | PASS | 0.724 | postgres-junit.xml
TC-23 | test_all_required_filter_dimensions_real_source[blocked] | PASS | 0.971 | postgres-junit.xml
TC-24 | test_selected_traceability_reuses_original_ifc_source_and_derived_membership | PASS | 0.962 | postgres-junit.xml
TC-25 | test_read_queries_are_zero_business_writes_and_preserve_all_source_authorities | PASS | 3.887 | postgres-junit.xml
TC-26 | test_accepted_schedule_mapping_and_source_snapshot_immutable | PASS | 4.483 | regression-junit.xml
TC-27 | test_xml_export_manifest_and_actual_source_roundtrip_with_no_cpm_claim | PASS | 5.886 | regression-junit.xml
TC-28 | test_two_successor_baselines_same_source_cannot_approve_stale_predecessor | PASS | 13.312 | regression-junit.xml
TC-29 | test_schedule_commands_do_not_create_scope_plan_or_derived_authorities | PASS | 7.241 | regression-junit.xml
TC-30 | test_real_schedule_source_data_date_wbs_activities_calendars_and_hash[xml] | PASS | 0.011 | regression-junit.xml
TC-31 | test_real_schedule_source_data_date_wbs_activities_calendars_and_hash[xer] | PASS | 0.014 | regression-junit.xml
TC-32 | test_source_float_criticality_and_percent_complete_unknown_are_not_inferred | PASS | 0.032 | regression-junit.xml
TC-33 | test_invalid_source_numbers_or_units_are_not_coerced_into_valid_quantity[NaN-SOURCE_NUMBER_INVALID] | PASS | 0.013 | regression-junit.xml
TC-34 | test_invalid_source_numbers_or_units_are_not_coerced_into_valid_quantity[Infinity-SOURCE_NUMBER_INVALID] | PASS | 0.01 | regression-junit.xml
TC-35 | test_invalid_source_numbers_or_units_are_not_coerced_into_valid_quantity[PT2H-SOURCE_NUMBER_INVALID] | PASS | 0.012 | regression-junit.xml
TC-36 | test_invalid_source_numbers_or_units_are_not_coerced_into_valid_quantity[-1-DURATION_NEGATIVE] | PASS | 0.013 | regression-junit.xml
TC-37 | test_structural_and_source_validation_failure_cases[duplicate-<lambda>-ACTIVITIES_DUPLICATE_ID] | PASS | 0.011 | regression-junit.xml
TC-38 | test_structural_and_source_validation_failure_cases[missing_date-<lambda>-DATA_DATE_REQUIRED] | PASS | 0.012 | regression-junit.xml
TC-39 | test_structural_and_source_validation_failure_cases[invalid_date-<lambda>-DATA_DATE_INVALID] | PASS | 0.011 | regression-junit.xml
TC-40 | test_structural_and_source_validation_failure_cases[wbs_cycle-<lambda>-WBS_HIERARCHY_CYCLE] | PASS | 0.015 | regression-junit.xml
TC-41 | test_structural_and_source_validation_failure_cases[dangling_wbs-<lambda>-ACTIVITY_WBS_UNRESOLVED] | PASS | 0.012 | regression-junit.xml
TC-42 | test_structural_and_source_validation_failure_cases[unknown_relation-<lambda>-RELATIONSHIP_TYPE_UNSUPPORTED] | PASS | 0.012 | regression-junit.xml
TC-43 | test_structural_and_source_validation_failure_cases[invalid_activity_date-<lambda>-ACTIVITY_DATE_INVALID] | PASS | 0.014 | regression-junit.xml
TC-44 | test_structural_and_source_validation_failure_cases[invalid_percent-<lambda>-IMPORTED_PERCENT_COMPLETE_OUT_OF_RANGE] | PASS | 0.011 | regression-junit.xml
TC-45 | test_structural_and_source_validation_failure_cases[dangling_code-<lambda>-ACTIVITY_CODE_ASSIGNMENT_UNRESOLVED] | PASS | 0.011 | regression-junit.xml
TC-46 | test_invalid_xml_container_and_entity_source_rejected[] | PASS | 0.004 | regression-junit.xml
TC-47 | test_invalid_xml_container_and_entity_source_rejected[garbage] | PASS | 0.004 | regression-junit.xml
TC-48 | test_invalid_xml_container_and_entity_source_rejected[<bad] | PASS | 0.003 | regression-junit.xml
TC-49 | test_invalid_xml_container_and_entity_source_rejected[<Project/>] | PASS | 0.003 | regression-junit.xml
TC-50 | test_invalid_xml_container_and_entity_source_rejected[<!DOCTYPE x [<!ENTITY y 'bad'>]><APIBusinessObjects>&y;</APIBusinessObjects>] | PASS | 0.003 | regression-junit.xml
TC-51 | test_identity_based_diff_preserves_mapping_impacts_and_source_immutability | PASS | 0.017 | regression-junit.xml
TC-52 | test_untrusted_draft_identity_labels_and_metadata_return_validation_not_500[activities-source_fields-None] | PASS | 0.012 | regression-junit.xml
TC-53 | test_untrusted_draft_identity_labels_and_metadata_return_validation_not_500[activities-source_fields-value11] | PASS | 0.01 | regression-junit.xml
TC-54 | test_untrusted_draft_identity_labels_and_metadata_return_validation_not_500[calendars-source_fields-not a dictionary] | PASS | 0.017 | regression-junit.xml
TC-55 | test_boolean_relationship_lag_is_not_a_numeric_source_duration[True] | PASS | 0.015 | regression-junit.xml
TC-56 | test_boolean_relationship_lag_is_not_a_numeric_source_duration[False] | PASS | 0.012 | regression-junit.xml
TC-57 | test_ifc_real_geometry_quantities_psets_materials_and_source_hash | PASS | 10.207 | regression-junit.xml
TC-58 | test_ifc_invalid_sources_fail_closed[bad-bad.ifc-IFC_CONTAINER_INVALID] | PASS | 0.006 | regression-junit.xml
TC-59 | test_ifc_invalid_sources_fail_closed[-empty.ifc-EMPTY_SOURCE] | PASS | 0.003 | regression-junit.xml
TC-60 | test_ifc_invalid_sources_fail_closed[bad-bad.txt-UNSUPPORTED_SOURCE_FORMAT] | PASS | 0.003 | regression-junit.xml
TC-61 | test_excel_duplicate_scope_code_source_row_and_cycle_detection | PASS | 0.015 | regression-junit.xml
TC-62 | test_excel_formulas_and_external_links_not_imported_as_literal_scope[option0-FORMULA_SOURCE_NOT_SUPPORTED] | PASS | 0.014 | regression-junit.xml
TC-63 | test_excel_csv_fixture_valid_without_any_ifc_source | PASS | 0.035 | regression-junit.xml
TC-64 | test_excel_invalid_formats_and_empty_sources_are_reviewable_failure[bad.xlsx-bad] | PASS | 0.003 | regression-junit.xml
TC-65 | test_excel_invalid_formats_and_empty_sources_are_reviewable_failure[old.xls-bad] | PASS | 0.004 | regression-junit.xml
TC-66 | test_excel_invalid_formats_and_empty_sources_are_reviewable_failure[empty.xlsx-] | PASS | 0.004 | regression-junit.xml
TC-67 | test_real_ifc_version_acceptance_source_bytes_and_mn_scope_mapping | PASS | 4.661 | regression-junit.xml
TC-68 | test_plan_many_to_many_group_split_recompose_and_derived_lineage | PASS | 8.065 | regression-junit.xml
TC-69 | test_excel_native_staging_idempotent_candidate_and_preserved_source_quantity | PASS | 4.791 | regression-junit.xml
TC-70 | test_excel_direct_item_creation_rejects_silent_source_unit_conversion | PASS | 5.314 | regression-junit.xml
TC-71 | test_model_successor_diff_reject_and_prior_source_immutable | PASS | 7.943 | regression-junit.xml
TC-72 | test_source_model_cross_project_and_tenant_queries_denied | PASS | 4.127 | regression-junit.xml
TC-73 | test_approved_change_source_contract_consumes_bound_existing_authority_only | PASS | 4.049 | regression-junit.xml
TC-74 | application navigation composition uses one strategic source and preserves the alternate project/commercial modules | PASS | 0.0086779 | frontend-components.json
TC-75 | AWP canonical project presentation does not permit release when readiness source hashes are stale | PASS | 0.12217 | frontend-components.json
TC-76 | O1B-B frontend contracts — component tests are not real-browser release evidence keeps WBS hierarchy separate from Scope hierarchy and handles orphan source parents | PASS | 0.068927 | frontend-components.json
TC-77 | O1B-B frontend contracts — component tests are not real-browser release evidence preserves missing float as UNKNOWN and actual zero or false as source values | PASS | 0.30765 | frontend-components.json
TC-78 | O1B-B frontend contracts — component tests are not real-browser release evidence keeps Activity Codes and constraints as distinct source collections | PASS | 0.14583 | frontend-components.json
TC-79 | O1B-B frontend contracts — component tests are not real-browser release evidence uses native manifest fields and downloads the actual source file name | PASS | 0.046184 | frontend-components.json
TC-80 | 4D source fidelity and display uses explicit scalar query filters without sending empty values | PASS | 0.013378 | frontend-components.json
TC-81 | 4D source fidelity and display preserves hidden REMOVE/TEMPORARY even when blocked and styled | PASS | 0.0065251 | frontend-components.json
TC-82 | 4D source fidelity and display does not let invalid color or opacity configure domain visibility | PASS | 0.0081305 | frontend-components.json
TC-83 | 4D source fidelity and display steps explicit date across month/year boundaries, never substitutes today | PASS | 0.51707 | frontend-components.json
TC-84 | 4D source fidelity and display lists only accepted current and approved baselines, using actual Data Date | PASS | 2.1851 | frontend-components.json
TC-85 | 4D source fidelity and display uses server filters for Package, WBS, Scope and Plan and exposes 16 filters | PASS | 0.75899 | frontend-components.json
TC-86 | 4D source fidelity and display requests traceability through the authorized source-aware GET port | PASS | 0.90304 | frontend-components.json
TC-87 | 4D source fidelity and display compares baseline/current on the same selected date without a write command | PASS | 0.50238 | frontend-components.json
TC-88 | 4D source fidelity and display blocks missing accepted sources instead of silently previewing staging | PASS | 0.10549 | frontend-components.json
UI-1 | FOUR_D_ORIGINAL_IFC_REAL_GEOMETRY_ALL_NATURES_READINESS_OVERLAY | PASS |  | chromium/browser-uat.json
UI-2 | FOUR_D_FILTER_AND_IFC_SCOPE_PLAN_PACKAGE_ACTIVITY_TRACEABILITY | PASS |  | chromium/browser-uat.json
UI-3 | FOUR_D_BROWSER_FILTER_WBS | PASS |  | chromium/browser-uat.json
UI-4 | FOUR_D_BROWSER_FILTER_SCOPE | PASS |  | chromium/browser-uat.json
UI-5 | FOUR_D_BROWSER_FILTER_PLAN | PASS |  | chromium/browser-uat.json
UI-6 | FOUR_D_BROWSER_FILTER_PACKAGE | PASS |  | chromium/browser-uat.json
UI-7 | FOUR_D_ACTUAL_GEOMETRY_PICK_TRACEABILITY | PASS |  | chromium/browser-uat.json
UI-8 | FOUR_D_BROWSER_PLAY_PAUSE_SPEED_STEPS_AND_DATA_DATE | PASS |  | chromium/browser-uat.json

## 10_4D_State_Rules
Semánticas y estados 4D
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_tailored_types_are_ready_without_auto_release[TEMPORARY_WORKS] | PASS | 0.006 | postgres-junit.xml
TC-2 | test_due_date_never_clears_blocker[OPEN] | PASS | 0.005 | postgres-junit.xml
TC-3 | test_due_date_never_clears_blocker[IN_PROGRESS] | PASS | 0.005 | postgres-junit.xml
TC-4 | test_governed_package_types_without_dates[EWP] | PASS | 0.883 | postgres-junit.xml
TC-5 | test_governed_package_types_without_dates[PWP] | PASS | 0.81 | postgres-junit.xml
TC-6 | test_governed_package_types_without_dates[CWP] | PASS | 0.767 | postgres-junit.xml
TC-7 | test_governed_package_types_without_dates[IWP] | PASS | 0.428 | postgres-junit.xml
TC-8 | test_governed_package_types_without_dates[TWP] | PASS | 0.461 | postgres-junit.xml
TC-9 | test_governed_package_types_without_dates[SUPPORT] | PASS | 0.306 | postgres-junit.xml
TC-10 | test_governed_package_types_without_dates[LOGISTICS] | PASS | 1.147 | postgres-junit.xml
TC-11 | test_governed_package_types_without_dates[TEMPORARY_WORKS] | PASS | 0.554 | postgres-junit.xml
TC-12 | test_governed_constraint_types_preserve_due_date_no_auto_clear[ENGINEERING] | PASS | 0.292 | postgres-junit.xml
TC-13 | test_governed_constraint_types_preserve_due_date_no_auto_clear[PROCUREMENT] | PASS | 0.255 | postgres-junit.xml
TC-14 | test_governed_constraint_types_preserve_due_date_no_auto_clear[MATERIAL] | PASS | 0.289 | postgres-junit.xml
TC-15 | test_governed_constraint_types_preserve_due_date_no_auto_clear[LOGISTICS] | PASS | 0.222 | postgres-junit.xml
TC-16 | test_governed_constraint_types_preserve_due_date_no_auto_clear[ACCESS] | PASS | 0.267 | postgres-junit.xml
TC-17 | test_governed_constraint_types_preserve_due_date_no_auto_clear[WORKFRONT] | PASS | 0.331 | postgres-junit.xml
TC-18 | test_governed_constraint_types_preserve_due_date_no_auto_clear[PREDECESSOR] | PASS | 1.099 | postgres-junit.xml
TC-19 | test_governed_constraint_types_preserve_due_date_no_auto_clear[PERMIT] | PASS | 0.955 | postgres-junit.xml
TC-20 | test_governed_constraint_types_preserve_due_date_no_auto_clear[QUALITY] | PASS | 1.028 | postgres-junit.xml
TC-21 | test_governed_constraint_types_preserve_due_date_no_auto_clear[HSE] | PASS | 0.318 | postgres-junit.xml
TC-22 | test_governed_constraint_types_preserve_due_date_no_auto_clear[RESOURCE] | PASS | 0.294 | postgres-junit.xml
TC-23 | test_governed_constraint_types_preserve_due_date_no_auto_clear[EQUIPMENT] | PASS | 0.261 | postgres-junit.xml
TC-24 | test_governed_constraint_types_preserve_due_date_no_auto_clear[TEMPORARY_WORKS] | PASS | 0.261 | postgres-junit.xml
TC-25 | test_governed_constraint_types_preserve_due_date_no_auto_clear[INTERFACE] | PASS | 0.344 | postgres-junit.xml
TC-26 | test_governed_constraint_types_preserve_due_date_no_auto_clear[CLIENT_DECISION] | PASS | 0.262 | postgres-junit.xml
TC-27 | test_governed_constraint_types_preserve_due_date_no_auto_clear[CONTRACTUAL] | PASS | 0.282 | postgres-junit.xml
TC-28 | test_governed_constraint_types_preserve_due_date_no_auto_clear[OTHER] | PASS | 0.284 | postgres-junit.xml
TC-29 | test_all_non_temporary_nature_states[INSTALL-2026-10-20-NOT_STARTED-FUTURE_NOT_INSTALLED-False] | PASS | 0.063 | postgres-junit.xml
TC-30 | test_all_non_temporary_nature_states[INSTALL-2026-10-22-IN_PROGRESS-INSTALLATION-True] | PASS | 0.005 | postgres-junit.xml
TC-31 | test_all_non_temporary_nature_states[INSTALL-2026-10-24-COMPLETED-INSTALLED-True] | PASS | 0.005 | postgres-junit.xml
TC-32 | test_all_non_temporary_nature_states[REMOVE-2026-10-20-NOT_STARTED-EXISTING-True] | PASS | 0.005 | postgres-junit.xml
TC-33 | test_all_non_temporary_nature_states[REMOVE-2026-10-22-IN_PROGRESS-REMOVAL-True] | PASS | 0.004 | postgres-junit.xml
TC-34 | test_all_non_temporary_nature_states[REMOVE-2026-10-24-REMOVED-REMOVED-False] | PASS | 0.005 | postgres-junit.xml
TC-35 | test_all_non_temporary_nature_states[MAINTENANCE-2026-10-20-NOT_STARTED-EXISTING_IN_SERVICE-True] | PASS | 0.005 | postgres-junit.xml
TC-36 | test_all_non_temporary_nature_states[MAINTENANCE-2026-10-22-MAINTENANCE-MAINTENANCE_INTERVENTION-True] | PASS | 0.007 | postgres-junit.xml
TC-37 | test_all_non_temporary_nature_states[MAINTENANCE-2026-10-24-COMPLETED-RESTORED_IN_SERVICE-True] | PASS | 0.01 | postgres-junit.xml
TC-38 | test_temporary_explicit_multi_activity_boundaries[2026-09-30-NOT_STARTED-ABSENT_BEFORE_INSTALL-False] | PASS | 0.006 | postgres-junit.xml
TC-39 | test_temporary_explicit_multi_activity_boundaries[2026-10-01-IN_PROGRESS-TEMPORARY_INSTALLATION-True] | PASS | 0.004 | postgres-junit.xml
TC-40 | test_temporary_explicit_multi_activity_boundaries[2026-10-03-TEMPORARY-TEMPORARY_IN_USE-True] | PASS | 0.005 | postgres-junit.xml
TC-41 | test_temporary_explicit_multi_activity_boundaries[2026-10-09-TEMPORARY-TEMPORARY_IN_USE-True] | PASS | 0.003 | postgres-junit.xml
TC-42 | test_temporary_explicit_multi_activity_boundaries[2026-10-10-IN_PROGRESS-TEMPORARY_REMOVAL-True] | PASS | 0.005 | postgres-junit.xml
TC-43 | test_temporary_explicit_multi_activity_boundaries[2026-10-12-REMOVED-ABSENT_AFTER_REMOVAL-False] | PASS | 0.006 | postgres-junit.xml
TC-44 | test_temporary_never_guesses_names_or_missing_phases[activities0-TEMPORARY_INSTALL_REMOVE_PHASES_REQUIRED] | PASS | 0.007 | postgres-junit.xml
TC-45 | test_temporary_never_guesses_names_or_missing_phases[activities1-TEMPORARY_EXPLICIT_PHASE_REQUIRED] | PASS | 0.005 | postgres-junit.xml
TC-46 | test_temporary_never_guesses_names_or_missing_phases[activities2-TEMPORARY_PHASE_ORDER_INVALID] | PASS | 0.006 | postgres-junit.xml
TC-47 | test_missing_broken_date_or_phase_is_not_healthy_completion[activities0-ACTIVITY_MAPPING_REQUIRED] | PASS | 0.005 | postgres-junit.xml
TC-48 | test_missing_broken_date_or_phase_is_not_healthy_completion[activities1-ACTIVITY_DATES_INCOMPLETE] | PASS | 0.003 | postgres-junit.xml
TC-49 | test_missing_broken_date_or_phase_is_not_healthy_completion[activities2-ACTIVITY_DATES_INCOMPLETE] | PASS | 0.003 | postgres-junit.xml
TC-50 | test_missing_broken_date_or_phase_is_not_healthy_completion[activities3-ACTIVITY_DATE_ORDER_INVALID] | PASS | 0.003 | postgres-junit.xml
TC-51 | test_missing_broken_date_or_phase_is_not_healthy_completion[activities4-ACTIVITY_PHASE_INVALID] | PASS | 0.004 | postgres-junit.xml
TC-52 | test_many_activities_resolve_membership_envelope_without_creating_dates | PASS | 0.003 | postgres-junit.xml
TC-53 | test_actual_dates_current_and_planned_baseline_are_distinct_sources | PASS | 0.003 | postgres-junit.xml
TC-54 | test_scheduled_readiness_overlay_does_not_modify_schedule_state_or_logic | PASS | 0.003 | postgres-junit.xml
TC-55 | test_delayed_overlay_only_explicit_data_date_and_known_imported_status[Not Started] | PASS | 0.003 | postgres-junit.xml
TC-56 | test_delayed_overlay_only_explicit_data_date_and_known_imported_status[NOT_STARTED] | PASS | 0.003 | postgres-junit.xml
TC-57 | test_delayed_overlay_only_explicit_data_date_and_known_imported_status[In Progress] | PASS | 0.003 | postgres-junit.xml
TC-58 | test_delayed_overlay_only_explicit_data_date_and_known_imported_status[IN_PROGRESS] | PASS | 0.003 | postgres-junit.xml
TC-59 | test_milestone_one_declared_date_is_valid_without_duration_calculation | PASS | 0.004 | postgres-junit.xml
TC-60 | test_semantic_comparison_no_forecast_cpm[2026-10-20-2026-10-20-ALIGNED] | PASS | 0.005 | postgres-junit.xml
TC-61 | test_semantic_comparison_no_forecast_cpm[2026-10-24-2026-10-20-BEHIND_BASELINE] | PASS | 0.006 | postgres-junit.xml
TC-62 | test_semantic_comparison_no_forecast_cpm[2026-10-20-2026-10-24-AHEAD_OF_BASELINE] | PASS | 0.008 | postgres-junit.xml
TC-63 | test_profile_permits_presentation_but_not_rewriting_scope_semantics | PASS | 0.011 | postgres-junit.xml
TC-64 | test_profile_invalid_authority_flags_rejected[temporary_phase_policy-GUESS_NAME] | PASS | 0.005 | postgres-junit.xml
TC-65 | test_current_source_explicit_data_date_and_governed_sources_only | PASS | 56.328 | postgres-junit.xml
TC-66 | test_explicit_control_period_association_does_not_substitute_cutoff_for_data_date | PASS | 3.432 | postgres-junit.xml
TC-67 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[INSTALL-2026-10-22T08:00:00-NOT_STARTED-FUTURE_NOT_INSTALLED] | PASS | 1.008 | postgres-junit.xml
TC-68 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[INSTALL-2026-10-23T12:00:00-IN_PROGRESS-INSTALLATION] | PASS | 0.827 | postgres-junit.xml
TC-69 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[INSTALL-2026-10-25T08:00:00-COMPLETED-INSTALLED] | PASS | 0.948 | postgres-junit.xml
TC-70 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[REMOVE-2026-10-22T08:00:00-NOT_STARTED-EXISTING] | PASS | 0.729 | postgres-junit.xml
TC-71 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[REMOVE-2026-10-23T12:00:00-IN_PROGRESS-REMOVAL] | PASS | 0.946 | postgres-junit.xml
TC-72 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[REMOVE-2026-10-25T08:00:00-REMOVED-REMOVED] | PASS | 0.883 | postgres-junit.xml
TC-73 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[TEMPORARY-2026-10-20T08:00:00-NOT_STARTED-ABSENT_BEFORE_INSTALL] | PASS | 0.675 | postgres-junit.xml
TC-74 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[TEMPORARY-2026-10-21T12:00:00-IN_PROGRESS-TEMPORARY_INSTALLATION] | PASS | 0.627 | postgres-junit.xml
TC-75 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[TEMPORARY-2026-10-22T12:00:00-TEMPORARY-TEMPORARY_IN_USE] | PASS | 0.871 | postgres-junit.xml
TC-76 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[TEMPORARY-2026-10-25T12:00:00-IN_PROGRESS-TEMPORARY_REMOVAL] | PASS | 0.978 | postgres-junit.xml
TC-77 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[TEMPORARY-2026-10-26T08:00:00-REMOVED-ABSENT_AFTER_REMOVAL] | PASS | 0.992 | postgres-junit.xml
TC-78 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[MAINTENANCE-2026-10-22T08:00:00-NOT_STARTED-EXISTING_IN_SERVICE] | PASS | 0.797 | postgres-junit.xml
TC-79 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[MAINTENANCE-2026-10-23T12:00:00-MAINTENANCE-MAINTENANCE_INTERVENTION] | PASS | 0.666 | postgres-junit.xml
TC-80 | test_four_nature_semantics_real_ifc_plan_awp_activity_chain[MAINTENANCE-2026-10-25T08:00:00-COMPLETED-RESTORED_IN_SERVICE] | PASS | 0.768 | postgres-junit.xml
TC-81 | test_baseline_current_same_date_comparison_exposes_variance_no_cpm | PASS | 2.778 | postgres-junit.xml
TC-82 | test_all_required_filter_dimensions_real_source[scope_nature] | PASS | 0.957 | postgres-junit.xml
TC-83 | test_readiness_blocker_is_separate_from_imported_scheduled_state | PASS | 1.061 | postgres-junit.xml
TC-84 | test_version_create_requires_register_etag_and_preserves_explicit_data_date | PASS | 0.928 | regression-junit.xml
TC-85 | test_manual_creation_cannot_forge_cpm_results_and_updates_create_new_version | PASS | 1.247 | regression-junit.xml
TC-86 | test_explicit_period_association_preserves_data_date_distinct_from_cutoff | PASS | 4.664 | regression-junit.xml
TC-87 | test_real_schedule_source_data_date_wbs_activities_calendars_and_hash[xml] | PASS | 0.011 | regression-junit.xml
TC-88 | test_real_schedule_source_data_date_wbs_activities_calendars_and_hash[xer] | PASS | 0.014 | regression-junit.xml
TC-89 | test_xml_constraints_primary_and_secondary_preserve_types_and_dates | PASS | 0.018 | regression-junit.xml
TC-90 | test_xml_export_is_actual_xml_parser_loop_with_core_semantics_and_no_native_baseline_claim | PASS | 0.031 | regression-junit.xml
TC-91 | test_structural_and_source_validation_failure_cases[missing_date-<lambda>-DATA_DATE_REQUIRED] | PASS | 0.012 | regression-junit.xml
TC-92 | test_structural_and_source_validation_failure_cases[invalid_date-<lambda>-DATA_DATE_INVALID] | PASS | 0.011 | regression-junit.xml
TC-93 | test_structural_and_source_validation_failure_cases[invalid_activity_date-<lambda>-ACTIVITY_DATE_INVALID] | PASS | 0.014 | regression-junit.xml
TC-94 | test_excel_each_scope_nature_has_independent_semantics[INSTALL] | PASS | 0.009 | regression-junit.xml
TC-95 | test_excel_each_scope_nature_has_independent_semantics[REMOVE] | PASS | 0.007 | regression-junit.xml
TC-96 | test_excel_each_scope_nature_has_independent_semantics[TEMPORARY] | PASS | 0.013 | regression-junit.xml
TC-97 | test_excel_each_scope_nature_has_independent_semantics[MAINTENANCE] | PASS | 0.007 | regression-junit.xml
TC-98 | test_excel_invalid_governed_values_block_candidate[Scope Nature-BUILD_WHATEVER-INVALID_SCOPE_NATURE] | PASS | 0.007 | regression-junit.xml
TC-99 | test_excel_invalid_governed_values_block_candidate[Unit-unknown-INVALID_UNIT] | PASS | 0.016 | regression-junit.xml
TC-100 | test_excel_invalid_governed_values_block_candidate[Quantity-NaN-INVALID_QUANTITY] | PASS | 0.011 | regression-junit.xml
TC-101 | test_excel_invalid_governed_values_block_candidate[Quantity-Infinity-INVALID_QUANTITY] | PASS | 0.009 | regression-junit.xml
TC-102 | test_excel_invalid_governed_values_block_candidate[Quantity--3-INVALID_QUANTITY] | PASS | 0.009 | regression-junit.xml
TC-103 | test_excel_invalid_governed_values_block_candidate[Quantity-1,000-INVALID_QUANTITY] | PASS | 0.01 | regression-junit.xml
TC-104 | test_excel_invalid_governed_values_block_candidate[Parent Scope Code-absent-MISSING_PARENT] | PASS | 0.011 | regression-junit.xml
TC-105 | test_excel_invalid_governed_values_block_candidate[Scope Type-COST_BASELINE-INVALID_SCOPE_TYPE] | PASS | 0.008 | regression-junit.xml
TC-106 | test_manual_scope_natures_and_quantities[INSTALL] | PASS | 16.427 | regression-junit.xml
TC-107 | test_manual_scope_natures_and_quantities[REMOVE] | PASS | 3.332 | regression-junit.xml
TC-108 | test_manual_scope_natures_and_quantities[TEMPORARY] | PASS | 4.133 | regression-junit.xml
TC-109 | test_manual_scope_natures_and_quantities[MAINTENANCE] | PASS | 4.58 | regression-junit.xml
TC-110 | test_revision_sod_and_candidate_edit_after_preparation | PASS | 4.047 | regression-junit.xml
TC-111 | test_postgresql_baseline_raw_update_rejected | PASS | 4.27 | regression-junit.xml
TC-112 | test_excel_native_staging_idempotent_candidate_and_preserved_source_quantity | PASS | 4.791 | regression-junit.xml
TC-113 | test_plan_publication_revalidates_current_scope_after_approved_successor | PASS | 5.367 | regression-junit.xml
TC-114 | test_strategy_ordered_parallel_publication_successor_and_candidate_segmentation[AREA] | PASS | 6.068 | regression-junit.xml
TC-115 | test_strategy_ordered_parallel_publication_successor_and_candidate_segmentation[ZONE] | PASS | 5.197 | regression-junit.xml
TC-116 | test_strategy_ordered_parallel_publication_successor_and_candidate_segmentation[SYSTEM] | PASS | 9.632 | regression-junit.xml
TC-117 | test_strategy_ordered_parallel_publication_successor_and_candidate_segmentation[QUANTITY_RANGE] | PASS | 8.317 | regression-junit.xml
TC-118 | O1B-B frontend contracts — component tests are not real-browser release evidence associates period explicitly without forcing Data Date to cutoff | PASS | 0.097102 | frontend-components.json
TC-119 | 4D source fidelity and display preserves hidden REMOVE/TEMPORARY even when blocked and styled | PASS | 0.0065251 | frontend-components.json
TC-120 | 4D source fidelity and display steps explicit date across month/year boundaries, never substitutes today | PASS | 0.51707 | frontend-components.json
TC-121 | 4D source fidelity and display lists only accepted current and approved baselines, using actual Data Date | PASS | 2.1851 | frontend-components.json
TC-122 | 4D source fidelity and display compares baseline/current on the same selected date without a write command | PASS | 0.50238 | frontend-components.json
UI-1 | 4D State Profiles_ADMIN_INDEPENDENT_PUBLICATION | PASS |  | chromium/browser-uat.json
UI-2 | FOUR_D_ORIGINAL_IFC_REAL_GEOMETRY_ALL_NATURES_READINESS_OVERLAY | PASS |  | chromium/browser-uat.json
UI-3 | BASELINE_CURRENT_COMPARISON_EXPLICIT_DATA_DATE | PASS |  | chromium/browser-uat.json
UI-4 | FOUR_D_BROWSER_PLAY_PAUSE_SPEED_STEPS_AND_DATA_DATE | PASS |  | chromium/browser-uat.json

## 11_Admin_User
Configuración y operación
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_no_scope_mapping_blocks_and_profile_can_require_activity | PASS | 0.005 | postgres-junit.xml
TC-2 | test_profile_sod_and_published_immutable | PASS | 0.756 | postgres-junit.xml
TC-3 | test_generic_admin_cannot_bypass_awp_governance[create] | PASS | 0.106 | postgres-junit.xml
TC-4 | test_generic_admin_cannot_bypass_awp_governance[patch] | PASS | 0.148 | postgres-junit.xml
TC-5 | test_generic_admin_cannot_bypass_awp_governance[publish] | PASS | 0.111 | postgres-junit.xml
TC-6 | test_generic_admin_cannot_bypass_awp_governance[clone] | PASS | 0.097 | postgres-junit.xml
TC-7 | test_last_material_profile_editor_cannot_publish_even_if_not_creator | PASS | 1.225 | postgres-junit.xml
TC-8 | test_package_manager_authority_cannot_bypass_release_sod[preparer] | PASS | 8.775 | postgres-junit.xml
TC-9 | test_package_manager_authority_cannot_bypass_release_sod[assessor] | PASS | 5.501 | postgres-junit.xml
TC-10 | test_profile_permits_presentation_but_not_rewriting_scope_semantics | PASS | 0.011 | postgres-junit.xml
TC-11 | test_profile_invalid_authority_flags_rejected[mapping_completeness_policy-IGNORE] | PASS | 0.006 | postgres-junit.xml
TC-12 | test_profile_invalid_authority_flags_rejected[temporary_phase_policy-GUESS_NAME] | PASS | 0.005 | postgres-junit.xml
TC-13 | test_profile_invalid_authority_flags_rejected[separation_of_duties-value2] | PASS | 0.005 | postgres-junit.xml
TC-14 | test_profile_invalid_authority_flags_rejected[allow_direct_scope_mapping-yes] | PASS | 0.011 | postgres-junit.xml
TC-15 | test_read_queries_are_zero_business_writes_and_preserve_all_source_authorities | PASS | 3.887 | postgres-junit.xml
TC-16 | test_configuration_sod_etag_idempotency_and_immutable_publication | PASS | 1.194 | postgres-junit.xml
TC-17 | test_register_idempotency_and_policy_type | PASS | 17.281 | regression-junit.xml
TC-18 | test_get_schedule_overview_and_profiles_have_no_sql_writes | PASS | 2.79 | regression-junit.xml
TC-19 | test_published_health_policy_checks_without_cpm[negative_lag-SCHEDULE_NEGATIVE_LAG-True] | PASS | 4.063 | regression-junit.xml
TC-20 | test_published_health_policy_checks_without_cpm[hard_constraint-SCHEDULE_HARD_CONSTRAINT-True] | PASS | 4.78 | regression-junit.xml
TC-21 | test_published_health_policy_checks_without_cpm[open_ends-SCHEDULE_OPEN_ENDS-True] | PASS | 6.23 | regression-junit.xml
TC-22 | test_published_health_policy_checks_without_cpm[missing_calendar-SCHEDULE_CALENDAR_REFERENCE_MISSING-True] | PASS | 5.058 | regression-junit.xml
TC-23 | test_published_health_policy_checks_without_cpm[long_duration-SCHEDULE_LONG_DURATION-False] | PASS | 5.331 | regression-junit.xml
TC-24 | test_published_health_policy_checks_without_cpm[excessive_lag-SCHEDULE_EXCESSIVE_LAG-False] | PASS | 5.423 | regression-junit.xml
TC-25 | test_invalid_authority_or_policy_is_rejected_before_persistence[calendar_handling-ASSUME_8_HOURS] | PASS | 0.176 | regression-junit.xml
TC-26 | test_invalid_authority_or_policy_is_rejected_before_persistence[lookahead_default_days-True] | PASS | 0.157 | regression-junit.xml
TC-27 | test_invalid_authority_or_policy_is_rejected_before_persistence[inherit_to_descendants-yes] | PASS | 0.158 | regression-junit.xml
TC-28 | test_invalid_authority_or_policy_is_rejected_before_persistence[near_critical_threshold-value3] | PASS | 0.154 | regression-junit.xml
TC-29 | test_invalid_authority_or_policy_is_rejected_before_persistence[near_critical_threshold-value4] | PASS | 0.171 | regression-junit.xml
TC-30 | test_invalid_authority_or_policy_is_rejected_before_persistence[open_end_policy-value5] | PASS | 0.163 | regression-junit.xml
TC-31 | test_invalid_authority_or_policy_is_rejected_before_persistence[mapping_policy-value6] | PASS | 0.159 | regression-junit.xml
TC-32 | test_invalid_authority_or_policy_is_rejected_before_persistence[allowed_constraints-value7] | PASS | 0.143 | regression-junit.xml
TC-33 | test_invalid_authority_or_policy_is_rejected_before_persistence[supported_exchange-value8] | PASS | 0.17 | regression-junit.xml
TC-34 | test_invalid_authority_or_policy_is_rejected_before_persistence[scope-value9] | PASS | 0.161 | regression-junit.xml
TC-35 | test_profile_publication_rejects_author_and_last_material_editor | PASS | 1.046 | regression-junit.xml
TC-36 | test_legacy_admin_cannot_bypass_governed_schedule_profile[create] | PASS | 0.07 | regression-junit.xml
TC-37 | test_legacy_admin_cannot_bypass_governed_schedule_profile[patch] | PASS | 0.053 | regression-junit.xml
TC-38 | test_legacy_admin_cannot_bypass_governed_schedule_profile[publish] | PASS | 0.044 | regression-junit.xml
TC-39 | test_legacy_admin_cannot_bypass_governed_schedule_profile[clone] | PASS | 0.044 | regression-junit.xml
TC-40 | test_schedule_commands_do_not_create_scope_plan_or_derived_authorities | PASS | 7.241 | regression-junit.xml
TC-41 | test_granular_roles_can_read_canonical_scope_without_broad_admin[scope_manager] | PASS | 2.872 | regression-junit.xml
TC-42 | test_granular_roles_can_read_canonical_scope_without_broad_admin[bim_manager] | PASS | 3.206 | regression-junit.xml
TC-43 | test_granular_roles_can_read_canonical_scope_without_broad_admin[bim_coordinator] | PASS | 3.056 | regression-junit.xml
TC-44 | test_granular_roles_can_read_canonical_scope_without_broad_admin[construction_manager] | PASS | 3.167 | regression-junit.xml
TC-45 | test_granular_roles_can_read_canonical_scope_without_broad_admin[document_controller] | PASS | 3.363 | regression-junit.xml
TC-46 | test_granular_roles_can_read_canonical_scope_without_broad_admin[manager] | PASS | 4.123 | regression-junit.xml
TC-47 | test_granular_roles_can_read_canonical_scope_without_broad_admin[executive] | PASS | 5.185 | regression-junit.xml
TC-48 | test_generic_admin_cannot_bypass_governed_scope_profile[create] | PASS | 3.02 | regression-junit.xml
TC-49 | test_generic_admin_cannot_bypass_governed_scope_profile[edit] | PASS | 2.829 | regression-junit.xml
TC-50 | test_generic_admin_cannot_bypass_governed_scope_profile[publish] | PASS | 4.293 | regression-junit.xml
TC-51 | test_generic_admin_cannot_bypass_governed_scope_profile[clone] | PASS | 2.687 | regression-junit.xml
TC-52 | test_scope_profile_latest_material_editor_cannot_self_publish | PASS | 2.772 | regression-junit.xml
TC-53 | test_approved_change_source_contract_consumes_bound_existing_authority_only | PASS | 4.049 | regression-junit.xml
TC-54 | application navigation composition reuses canonical Workspace navigation for Operational Setup and the existing ADMIN process configuration | PASS | 0.0096601 | frontend-components.json
TC-55 | application navigation composition does not duplicate strategic configuration under platform administration | PASS | 0.0025215 | frontend-components.json
TC-56 | application navigation composition projects Wave 2A USER transactions and ADMIN Bucket configuration from the canonical strategic blueprint | PASS | 0.0050425 | frontend-components.json
TC-57 | AWP canonical project presentation has separate CWA/packages/execution constraint/readiness navigation and no CPM authority | PASS | 1.4335 | frontend-components.json
TC-58 | AWP canonical project presentation renders mandatory dimensions from published policy and excludes unsupported evidence keys | PASS | 0.24299 | frontend-components.json
TC-59 | AWP canonical project presentation publishes configuration through governed feature API without user project writes | PASS | 0.38809 | frontend-components.json
TC-60 | O1B-B frontend contracts — component tests are not real-browser release evidence respects a profile disabling direct Scope mappings | PASS | 0.091902 | frontend-components.json
TC-61 | O1B-B frontend contracts — component tests are not real-browser release evidence renders safely before a Schedule Profile has been bound | PASS | 0.20872 | frontend-components.json
TC-62 | O1B-B frontend contracts — component tests are not real-browser release evidence ADMIN creates Schedule Profile through its dedicated guarded API | PASS | 0.15453 | frontend-components.json
TC-63 | 4D source fidelity and display requests traceability through the authorized source-aware GET port | PASS | 0.90304 | frontend-components.json
UI-1 | AWP Profiles_ADMIN_INDEPENDENT_PUBLICATION | PASS |  | chromium/browser-uat.json
UI-2 | 4D State Profiles_ADMIN_INDEPENDENT_PUBLICATION | PASS |  | chromium/browser-uat.json

## 12_Security
Ámbito permisos y separación de funciones
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Caso | Comprobación | Resultado | Tiempo s | Evidencia
TC-1 | test_cwa_container_hierarchy_and_cycle_etag | PASS | 36.132 | postgres-junit.xml
TC-2 | test_package_idempotency_rbac_tenant_project_and_missing_ifmatch | PASS | 0.978 | postgres-junit.xml
TC-3 | test_get_zero_business_writes | PASS | 2.733 | postgres-junit.xml
TC-4 | test_postgres_history_immutable[awp_package_mappings] | PASS | 0.029 | postgres-junit.xml
TC-5 | test_postgres_history_immutable[awp_constraint_mappings] | PASS | 0.035 | postgres-junit.xml
TC-6 | test_postgres_history_immutable[awp_readiness_assessments] | PASS | 0.021 | postgres-junit.xml
TC-7 | test_postgres_history_immutable[awp_history] | PASS | 0.021 | postgres-junit.xml
TC-8 | test_profile_sod_and_published_immutable | PASS | 0.756 | postgres-junit.xml
TC-9 | test_generic_admin_cannot_bypass_awp_governance[create] | PASS | 0.106 | postgres-junit.xml
TC-10 | test_generic_admin_cannot_bypass_awp_governance[patch] | PASS | 0.148 | postgres-junit.xml
TC-11 | test_generic_admin_cannot_bypass_awp_governance[publish] | PASS | 0.111 | postgres-junit.xml
TC-12 | test_generic_admin_cannot_bypass_awp_governance[clone] | PASS | 0.097 | postgres-junit.xml
TC-13 | test_package_manager_authority_cannot_bypass_release_sod[preparer] | PASS | 8.775 | postgres-junit.xml
TC-14 | test_package_manager_authority_cannot_bypass_release_sod[assessor] | PASS | 5.501 | postgres-junit.xml
TC-15 | test_postgres_mapping_rejects_cross_tenant_and_project_references | PASS | 0.444 | postgres-junit.xml
TC-16 | test_profile_invalid_authority_flags_rejected[mapping_completeness_policy-IGNORE] | PASS | 0.006 | postgres-junit.xml
TC-17 | test_profile_invalid_authority_flags_rejected[temporary_phase_policy-GUESS_NAME] | PASS | 0.005 | postgres-junit.xml
TC-18 | test_profile_invalid_authority_flags_rejected[separation_of_duties-value2] | PASS | 0.005 | postgres-junit.xml
TC-19 | test_profile_invalid_authority_flags_rejected[allow_direct_scope_mapping-yes] | PASS | 0.011 | postgres-junit.xml
TC-20 | test_read_queries_are_zero_business_writes_and_preserve_all_source_authorities | PASS | 3.887 | postgres-junit.xml
TC-21 | test_scope_tenant_and_read_only_rbac_isolation | PASS | 1.486 | postgres-junit.xml
TC-22 | test_configuration_sod_etag_idempotency_and_immutable_publication | PASS | 1.194 | postgres-junit.xml
TC-23 | test_register_idempotency_and_policy_type | PASS | 17.281 | regression-junit.xml
TC-24 | test_version_create_requires_register_etag_and_preserves_explicit_data_date | PASS | 0.928 | regression-junit.xml
TC-25 | test_mapping_wrong_tenant_project_and_unknown_external_identity_denied | PASS | 1.681 | regression-junit.xml
TC-26 | test_accepted_schedule_mapping_and_source_snapshot_immutable | PASS | 4.483 | regression-junit.xml
TC-27 | test_baseline_sod_and_database_immutability | PASS | 6.833 | regression-junit.xml
TC-28 | test_invalid_authority_or_policy_is_rejected_before_persistence[calendar_handling-ASSUME_8_HOURS] | PASS | 0.176 | regression-junit.xml
TC-29 | test_invalid_authority_or_policy_is_rejected_before_persistence[lookahead_default_days-True] | PASS | 0.157 | regression-junit.xml
TC-30 | test_invalid_authority_or_policy_is_rejected_before_persistence[inherit_to_descendants-yes] | PASS | 0.158 | regression-junit.xml
TC-31 | test_invalid_authority_or_policy_is_rejected_before_persistence[near_critical_threshold-value3] | PASS | 0.154 | regression-junit.xml
TC-32 | test_invalid_authority_or_policy_is_rejected_before_persistence[near_critical_threshold-value4] | PASS | 0.171 | regression-junit.xml
TC-33 | test_invalid_authority_or_policy_is_rejected_before_persistence[open_end_policy-value5] | PASS | 0.163 | regression-junit.xml
TC-34 | test_invalid_authority_or_policy_is_rejected_before_persistence[mapping_policy-value6] | PASS | 0.159 | regression-junit.xml
TC-35 | test_invalid_authority_or_policy_is_rejected_before_persistence[allowed_constraints-value7] | PASS | 0.143 | regression-junit.xml
TC-36 | test_invalid_authority_or_policy_is_rejected_before_persistence[supported_exchange-value8] | PASS | 0.17 | regression-junit.xml
TC-37 | test_invalid_authority_or_policy_is_rejected_before_persistence[scope-value9] | PASS | 0.161 | regression-junit.xml
TC-38 | test_profile_publication_rejects_author_and_last_material_editor | PASS | 1.046 | regression-junit.xml
TC-39 | test_legacy_admin_cannot_bypass_governed_schedule_profile[create] | PASS | 0.07 | regression-junit.xml
TC-40 | test_legacy_admin_cannot_bypass_governed_schedule_profile[patch] | PASS | 0.053 | regression-junit.xml
TC-41 | test_legacy_admin_cannot_bypass_governed_schedule_profile[publish] | PASS | 0.044 | regression-junit.xml
TC-42 | test_legacy_admin_cannot_bypass_governed_schedule_profile[clone] | PASS | 0.044 | regression-junit.xml
TC-43 | test_schedule_commands_do_not_create_scope_plan_or_derived_authorities | PASS | 7.241 | regression-junit.xml
TC-44 | test_utf16_dtd_cannot_bypass_utf8_entity_guard | PASS | 0.006 | regression-junit.xml
TC-45 | test_scope_hierarchy_draft_etag_and_immutable_baseline_successor | PASS | 7.304 | regression-junit.xml
TC-46 | test_revision_sod_and_candidate_edit_after_preparation | PASS | 4.047 | regression-junit.xml
TC-47 | test_generic_admin_cannot_bypass_governed_scope_profile[create] | PASS | 3.02 | regression-junit.xml
TC-48 | test_generic_admin_cannot_bypass_governed_scope_profile[edit] | PASS | 2.829 | regression-junit.xml
TC-49 | test_generic_admin_cannot_bypass_governed_scope_profile[publish] | PASS | 4.293 | regression-junit.xml
TC-50 | test_generic_admin_cannot_bypass_governed_scope_profile[clone] | PASS | 2.687 | regression-junit.xml
TC-51 | test_excel_native_staging_idempotent_candidate_and_preserved_source_quantity | PASS | 4.791 | regression-junit.xml
TC-52 | test_model_successor_diff_reject_and_prior_source_immutable | PASS | 7.943 | regression-junit.xml
TC-53 | test_source_model_cross_project_and_tenant_queries_denied | PASS | 4.127 | regression-junit.xml
TC-54 | test_approved_change_source_contract_consumes_bound_existing_authority_only | PASS | 4.049 | regression-junit.xml
TC-55 | AWP canonical project presentation has separate CWA/packages/execution constraint/readiness navigation and no CPM authority | PASS | 1.4335 | frontend-components.json
TC-56 | AWP canonical project presentation maps published Plan to existing Package with its own ETag and explicit phase | PASS | 0.63522 | frontend-components.json
TC-57 | O1B-B frontend contracts — component tests are not real-browser release evidence uses If-Match and idempotency on material commands | PASS | 0.0098551 | frontend-components.json
TC-58 | O1B-B frontend contracts — component tests are not real-browser release evidence does not offer editing mappings of an accepted immutable version | PASS | 0.05263 | frontend-components.json
TC-59 | 4D source fidelity and display requests traceability through the authorized source-aware GET port | PASS | 0.90304 | frontend-components.json

## 13_API
API de AWP readiness y 4D
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
Método | Ruta | Operación | Dominio
GET | /api/v1/awp/projects/{workspace_id}/overview | overview_api_v1_awp_projects__workspace_id__overview_get | AWP
GET | /api/v1/awp/projects/{workspace_id}/cwas | awp_list_cwas_api_v1_awp_projects__workspace_id__cwas_get | AWP
POST | /api/v1/awp/projects/{workspace_id}/cwas | create_cwa_api_v1_awp_projects__workspace_id__cwas_post | AWP
GET | /api/v1/awp/projects/{workspace_id}/packages | awp_list_packages_api_v1_awp_projects__workspace_id__packages_get | AWP
POST | /api/v1/awp/projects/{workspace_id}/packages | create_package_api_v1_awp_projects__workspace_id__packages_post | AWP
GET | /api/v1/awp/projects/{workspace_id}/mappings | awp_list_mappings_api_v1_awp_projects__workspace_id__mappings_get | AWP
GET | /api/v1/awp/projects/{workspace_id}/dependencies | awp_list_dependencies_api_v1_awp_projects__workspace_id__dependencies_get | AWP
POST | /api/v1/awp/projects/{workspace_id}/dependencies | create_dependency_api_v1_awp_projects__workspace_id__dependencies_post | AWP
GET | /api/v1/awp/projects/{workspace_id}/constraints | awp_list_constraints_api_v1_awp_projects__workspace_id__constraints_get | AWP
POST | /api/v1/awp/projects/{workspace_id}/constraints | create_constraint_api_v1_awp_projects__workspace_id__constraints_post | AWP
GET | /api/v1/awp/projects/{workspace_id}/constraint-mappings | awp_list_constraint_mappings_api_v1_awp_projects__workspace_id__constraint_mappings_get | AWP
GET | /api/v1/awp/projects/{workspace_id}/assessments | awp_list_assessments_api_v1_awp_projects__workspace_id__assessments_get | AWP
GET | /api/v1/awp/projects/{workspace_id}/history/{entity_type}/{identity} | history_api_v1_awp_projects__workspace_id__history__entity_type___identity__get | AWP
GET | /api/v1/awp/projects/{workspace_id}/packages/{identity} | package_detail_api_v1_awp_projects__workspace_id__packages__identity__get | AWP
PUT | /api/v1/awp/projects/{workspace_id}/packages/{identity} | update_package_api_v1_awp_projects__workspace_id__packages__identity__put | AWP
GET | /api/v1/awp/projects/{workspace_id}/cwas/{identity} | cwa_detail_api_v1_awp_projects__workspace_id__cwas__identity__get | AWP
PUT | /api/v1/awp/projects/{workspace_id}/cwas/{identity} | update_cwa_api_v1_awp_projects__workspace_id__cwas__identity__put | AWP
GET | /api/v1/awp/projects/{workspace_id}/constraints/{identity} | constraint_detail_api_v1_awp_projects__workspace_id__constraints__identity__get | AWP
PUT | /api/v1/awp/projects/{workspace_id}/constraints/{identity} | update_constraint_api_v1_awp_projects__workspace_id__constraints__identity__put | AWP
POST | /api/v1/awp/projects/{workspace_id}/packages/{identity}/transition | package_transition_api_v1_awp_projects__workspace_id__packages__identity__transition_post | AWP
POST | /api/v1/awp/projects/{workspace_id}/packages/{identity}/mappings | package_mapping_api_v1_awp_projects__workspace_id__packages__identity__mappings_post | AWP
PUT | /api/v1/awp/projects/{workspace_id}/dependencies/{identity} | update_dependency_api_v1_awp_projects__workspace_id__dependencies__identity__put | AWP
POST | /api/v1/awp/projects/{workspace_id}/constraints/{identity}/transition | constraint_transition_api_v1_awp_projects__workspace_id__constraints__identity__transition_post | AWP
POST | /api/v1/awp/projects/{workspace_id}/constraints/{identity}/mappings | constraint_mapping_api_v1_awp_projects__workspace_id__constraints__identity__mappings_post | AWP
POST | /api/v1/awp/projects/{workspace_id}/packages/{identity}/assess | assess_api_v1_awp_projects__workspace_id__packages__identity__assess_post | AWP
POST | /api/v1/awp/projects/{workspace_id}/packages/{identity}/release | release_api_v1_awp_projects__workspace_id__packages__identity__release_post | AWP
GET | /api/v1/awp/admin/profiles | profiles_api_v1_awp_admin_profiles_get | AWP
POST | /api/v1/awp/admin/profiles | create_profile_api_v1_awp_admin_profiles_post | AWP
PUT | /api/v1/awp/admin/profiles/{identity} | update_profile_api_v1_awp_admin_profiles__identity__put | AWP
POST | /api/v1/awp/admin/profiles/{identity}/publish | publish_profile_api_v1_awp_admin_profiles__identity__publish_post | AWP
POST | /api/v1/awp/admin/profiles/{identity}/successor | successor_profile_api_v1_awp_admin_profiles__identity__successor_post | AWP
GET | /api/v1/readiness/projects/{workspace_id}/workfront | workfront_api_v1_readiness_projects__workspace_id__workfront_get | Readiness
POST | /api/v1/readiness/projects/{workspace_id}/packages/{identity}/assess | assess_api_v1_readiness_projects__workspace_id__packages__identity__assess_post | Readiness
POST | /api/v1/readiness/projects/{workspace_id}/packages/{identity}/release | release_api_v1_readiness_projects__workspace_id__packages__identity__release_post | Readiness
GET | /api/v1/schedule/projects/{workspace_id}/4d | model_api_v1_schedule_projects__workspace_id__4d_get | 4D
GET | /api/v1/schedule/projects/{workspace_id}/4d/traceability/{identity} | traceability_api_v1_schedule_projects__workspace_id__4d_traceability__identity__get | 4D
GET | /api/v1/schedule/projects/{workspace_id}/4d/compare | compare_api_v1_schedule_projects__workspace_id__4d_compare_get | 4D
GET | /api/v1/schedule/4d/admin/profiles | profiles_api_v1_schedule_4d_admin_profiles_get | 4D
POST | /api/v1/schedule/4d/admin/profiles | create_profile_api_v1_schedule_4d_admin_profiles_post | 4D
PUT | /api/v1/schedule/4d/admin/profiles/{identity} | update_profile_api_v1_schedule_4d_admin_profiles__identity__put | 4D
POST | /api/v1/schedule/4d/admin/profiles/{identity}/publish | four_d_profile_publish_api_v1_schedule_4d_admin_profiles__identity__publish_post | 4D
POST | /api/v1/schedule/4d/admin/profiles/{identity}/successor | four_d_profile_successor_api_v1_schedule_4d_admin_profiles__identity__successor_post | 4D

## 14_Defects
Defectos y límites
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
ID | Severidad | Hallazgo | Estado | Tratamiento
B1-01 | S2 | Colisión de parámetros Path y Query impedía montar la ruta de trazabilidad | RESOLVED | Ruta corregida, importación y HTTP reales PASS
B1-02 | S1 | Guard PG leía un campo CWA inexistente en el historial de otros agregados | RESOLVED | IF por tipo de tabla; upgrade downgrade reupgrade y escrituras reales PASS
B1-03 | INFRA | Fallo de memoria al importar la suite en un contenedor adicional | RESOLVED | Runtime local contra PostgreSQL Docker aislado, sin cambiar resultados de negocio
LIM-01 | LIMIT | Sin XER export, native BaselineProject, XSD instalado, roundtrip Primavera ni P6 API | DECLARED_LIMIT | Límites anteriores conservados, sin prometer compatibilidad completa
LIM-02 | LIMIT | Sin ensayo de escala industrial, migración normal ni firmas de negocio | DECLARED_LIMIT | Mediciones locales y liberación técnica aislada

## 15_Release_Criteria
Criterios y mediciones de liberación
Corte técnico 21 octubre 2026
Validación técnica aislada sin firmas de aceptación de negocio
ID | Criterio u operación | Resultado | Muestras | Mín ms | Mediana ms | Máx ms | Evidencia
RC-01 | Existing O1B-B Schedule behavior preserved | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-02 | No Schedule rebuild | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-03 | CWA as area/container | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-04 | EWP | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-05 | PWP | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-06 | CWP | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-07 | IWP | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-08 | TWP | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-09 | SUPPORT configurable | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-10 | LOGISTICS configurable | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-11 | Scope ↔ Package M:N | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-12 | Plan ↔ Package M:N | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-13 | Package ↔ Activity M:N | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-14 | Package dependencies | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-15 | No rigid false AWP hierarchy | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-16 | ExecutionConstraint separate from P6 ScheduleConstraint | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-17 | Constraint types governed | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-18 | Blocking/nonblocking | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-19 | Constraint evidence/history | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-20 | Readiness assessment | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-21 | Workfront Readiness | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-22 | READY ≠ RELEASED | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-23 | Scheduled ≠ Ready | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-24 | Constraint does not silently change CPM logic | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-25 | Package mapping does not rewrite Schedule Version | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-26 | 4D Model | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-27 | Accepted Current source | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-28 | Approved Baseline source | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-29 | Baseline vs Current | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-30 | Data Date view | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-31 | INSTALL 4D semantics | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-32 | REMOVE 4D semantics | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-33 | TEMPORARY 4D semantics | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-34 | MAINTENANCE 4D semantics | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-35 | Plan/Package/Activity M:N works in 4D | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-36 | Derived 3D reused | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-37 | Original IFC unchanged | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-38 | Scope Baseline unchanged | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-39 | Schedule Baseline unchanged | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-40 | 4D filters | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-41 | 4D traceability | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-42 | Readiness/blocker overlay | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-43 | No native CPM engine | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-44 | No P6 API sync | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-45 | No duplicate Scope authority | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-46 | No duplicate Schedule authority | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-47 | ADMIN/USER separation | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-48 | RBAC | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-49 | SoD | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-50 | ETag | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-51 | Idempotency | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-52 | Audit | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-53 | PostgreSQL tests | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-54 | Chromium UAT | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-55 | Project 14 unchanged | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-56 | 0 open S1 | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
RC-57 | 0 open S2 | PASS |  |  |  |  | postgres-junit.xml; regression-junit.xml; browser-uat.json; api-observations.json
PERF-1 | CWA list | LOCAL_NO_SLA | 3 | 118.2193 | 130.6262 | 140.686 | Entorno aislado no escala productiva
PERF-2 | Package list | LOCAL_NO_SLA | 3 | 146.6009 | 148.1543 | 160.2087 | Entorno aislado no escala productiva
PERF-3 | Dependency list | LOCAL_NO_SLA | 3 | 92.6421 | 93.3792 | 95.5826 | Entorno aislado no escala productiva
PERF-4 | Execution Constraint list | LOCAL_NO_SLA | 3 | 104.6226 | 140.4458 | 147.942 | Entorno aislado no escala productiva
PERF-5 | Readiness assessment | LOCAL_NO_SLA | 1 | 746.3414 | 746.3414 | 746.3414 | Entorno aislado no escala productiva
PERF-6 | Package Scope mapping | LOCAL_NO_SLA | 1 | 446.1185 | 446.1185 | 446.1185 | Entorno aislado no escala productiva
PERF-7 | 4D initial API view | LOCAL_NO_SLA | 3 | 1004.6362 | 1296.4162 | 1454.6315 | Entorno aislado no escala productiva
PERF-8 | 4D date step API | LOCAL_NO_SLA | 3 | 773.3022 | 889.7695 | 1097.4251 | Entorno aislado no escala productiva
PERF-9 | 4D traceability | LOCAL_NO_SLA | 3 | 771.148 | 945.5575 | 1113.1894 | Entorno aislado no escala productiva
PERF-10 | 4D Baseline Current comparison | LOCAL_NO_SLA | 3 | 2190.2449 | 2355.412 | 2559.9101 | Entorno aislado no escala productiva