# Operational Macroprocess
Implementation Roadmap

P&Pmis Construction AI · Operational Macroprocess
Informe técnico de arquitectura · 19 de octubre de 2026

Secuencia de implementación propuesta, dependencias y criterios verificables para evolucionar la operación sin duplicar funcionalidades ni autoridades de P&Pmis.

Estado: PROPOSED_DESIGN. Arquitectura documental; no implementación de módulos, migración, liberación ni aceptación de negocio.

# 1. Decisión de secuencia y límites

El incremento presente termina con arquitectura y documentos. No ejecuta O1, no modifica módulos, no migra datos y no registra aceptación de negocio. La secuencia depende de autoridad de fuentes e identidad, no del orden del menú ni del ranking numérico.

Única siguiente implementación recomendada: WAVE O1 — PROJECT CONTROLS FOUNDATION. O1A resuelve primero el enlace canónico/legacy, autorización, período común y configuración. O1B establece baselines y adapters; O1C forecast/reporting. Evitar iniciar simultáneamente 25 módulos.

Aprobación del diseño habilita preparación/implementación acotada cuando se autorice, no operación productiva. Cada salida a uso vivo requiere aceptación/liberación autorizada y autorización aplicable del Project. El signoff estratégico de negocio sigue pendiente.

| Ola | Resultado objetivo | Nivel |
| --- | --- | --- |
| O1 · PROJECT CONTROLS FOUNDATION | O1A canonical identity binding and common period/policy first; O1A/O1B minimal document/evidence version references reused before any baseline approval; richer review/distribution/DMS integration remains O2; O1B approved Scope/Schedule/Cost baselines, adapters, typed Progress and Change/Risk/Issue foundation; O1C governed Forecast and source-consuming reporting | VERY_HIGH |
| O2 · PROCUREMENT / CONTRACTS / ENGINEERING | Reuse RFQ/bid primitives with configurable sourcing/award; Single Contract/PO/Commitment register; Engineering design packages/reviews; Lightweight Documents/external DMS references; Interfaces and long-lead readiness | VERY_HIGH |
| O3 · CONSTRUCTION EXECUTION | Field/workfront/daily capture; Optional AWP work-package release; Installed quantities/productivity/labor/equipment; Quality inspections/NCR/punch; HSE scoped internal capability or external system boundary | HIGH |
| O4 · CLAIMS / COMMISSIONING / HANDOVER / CLOSEOUT | Claims/delay/forensic governed evidence; Mechanical completion/pre-commissioning/commissioning; Turnover/handover and operational readiness; Asset data transition; Project closeout without deleting canonical identity | VERY_HIGH |

# 2. Mínimo viable y prerequisitos

Core O1: D01 contexto; D02 Scope; D03 Schedule; D04 Cost; D06 Progress; D07 Forecast; D08 Change; D09 Risk; D10 Issue; D14 evidencia mínima; D19 Project Controls/Reporting. D05 tarifas/horas y D12 compromiso se consumen bajo contrato mínimo de lectura; su suite completa no se adelanta artificialmente.

No incluye suite Field/QA/HSE, Engineering completa, sourcing/award/contratos completos, commissioning/handover, ERP/pagos ni DMS corporativo. No CPM nativo ni API/direct sync P6. Los registros operacionales existentes se preservan y exponen solo tras validar su vínculo y permisos.

O1A requiere resolver proyectos sin binding, colisiones de uno/múltiples legacy, pertenencia tenant, memberships y revocación/estado. Contractor/Direct no se fuerzan al Owner FID; Owner no puede saltar condiciones de compromiso porque esté ACTIVE. El contrato no cambia retroactivamente la autorización histórica.

# 3. O1 · PROJECT CONTROLS FOUNDATION

Alcance: O1A canonical identity binding and common period/policy first; O1A/O1B minimal document/evidence version references reused before any baseline approval; richer review/distribution/DMS integration remains O2; O1B approved Scope/Schedule/Cost baselines, adapters, typed Progress and Change/Risk/Issue foundation; O1C governed Forecast and source-consuming reporting.

Dependencias: Existing canonical creation/initialization/activation and scoped security; Upstream handoff/conditions contract; Explicit decision resolving projects.id versus canonical Workspace references; Approved P6/source-authority boundaries.

| Elemento | Definición / control propuesto |
| --- | --- |
| Entrada | Architecture and O1 design approved; Three route applicability and identity collision/access tests specified; Existing product/strategic baseline protected; No business signoff or release inferred from design approval |
| Salida / evidencia futura | Tested canonical binding with no duplicate Project; Published reusable period/mapping/progress/change configuration; Immutable approved baseline set and accepted schedule import provenance; Reconciled no-double-count Cost inputs and typed approved Progress; Versioned Forecast/report inputs with independent approvals and scoped access; Authorized business acceptance/release before live use |
| Riesgos | Identity-space mismatch; Legacy baseline overwrite and duration assumptions; Mixed progress/cost methods; Cross-domain currentness and scope leakage |
| Reutilización | Enterprise Workspace lifecycle/RBAC; ScheduleImport/raw metadata/maps; Scope/BIM quantities; CBS/control accounts/FBS; Existing minimal Document/evidence reference authority; Existing progress/change/forecast/snapshots |
| Complejidad relativa | VERY_HIGH. Sin fechas, horas, costo o dotación comprometidos. |

## O1A · HIGH

Resolve canonical identity adapter, owner boundaries, route authorization/current conditions and common control period/config policy before wider live reuse. Salida requerida: Executable approved design/tests for collision/missing mapping/access/status/conditions and period lifecycle; future schema changes explicitly authorized.

## O1B · VERY_HIGH

Implement narrowly approved source adapters/control baselines and typed scope/schedule/cost/progress/change/risk/issue foundation without native CPM or duplicate source authority. Salida requerida: Baseline/version/data-date/unit/mapping approvals; cost economic-origin rules and typed progress invariants verified.

## O1C · HIGH

Add versioned forecast and governed Project Controls reporting/look-ahead consuming approved source snapshots. Salida requerida: Reproducible ETC/EAC/time forecast assumptions and source references; no dashboard writes or baseline mutation.

Evidencia mínima de Document/version/hash se reutiliza antes de aprobar baseline en O1A/O1B. Reviews/distribución y DMS se amplían en O2. El contrato de compromiso/neteos en lectura es requisito del costo O1, aunque el hardening transaccional completo de D12 sea O2.

# 4. O2 · PROCUREMENT / CONTRACTS / ENGINEERING

Alcance: Reuse RFQ/bid primitives with configurable sourcing/award; Single Contract/PO/Commitment register; Engineering design packages/reviews; Lightweight Documents/external DMS references; Interfaces and long-lead readiness.

Dependencias: O1 canonical binding/period/baseline and Change foundation; Single-party/master-data decision; Approved obligation/call-off/netting/deduplication policy.

| Elemento | Definición / control propuesto |
| --- | --- |
| Entrada | O1 source-owner contracts proven; Procurement versus Contract Administration authority approved; Shared parties and source document references designed; Current strategic commercial/funding references remain upstream |
| Salida / evidencia futura | Award recommendation versus approval separated; One PO/Contract authority with legal variation history; No duplicated gross/net obligation or actual/accrual economic event; Engineering/document revisions and interface constraints traceable; Scoped SoD and audit/currentness verified |
| Riesgos | Duplicate menu/table authority; Award bypass or commitment condition bypass; Contract-client revenue mistaken for purchase cost; Full enterprise DMS scope creep |
| Reutilización | RFQPackage/RFQBid; Contract/PurchaseOrder/SOV; Notices/communications/certificates/receipts; Documents/transmittal primitives; Strategic Commercial and Funding references |
| Complejidad relativa | VERY_HIGH. Sin fechas, horas, costo o dotación comprometidos. |

# 5. O3 · CONSTRUCTION EXECUTION

Alcance: Field/workfront/daily capture; Optional AWP work-package release; Installed quantities/productivity/labor/equipment; Quality inspections/NCR/punch; HSE scoped internal capability or external system boundary.

Dependencias: O1 approved typed Progress/period/Change; O2 applicable engineering/material/document readiness; Package policy and source-owner integration contracts.

| Elemento | Definición / control propuesto |
| --- | --- |
| Entrada | Applicable source constraints and release criteria approved; Field evidence/measurement units and method configured; Quality/HSE internal versus external boundary decided |
| Salida / evidencia futura | Approved field progress/evidence feeds Progress once; Workfront/package readiness consumes current source constraints; Inspection/NCR/HSE status does not silently imply another owner approval; Audit/late-period adjustment and independent release tests pass |
| Riesgos | Physical/schedule/earned percent mixing; Unsafe release on stale technical/permit evidence; Universal AWP forced on unsuitable project types; Duplicate field/quality event capture |
| Reutilización | Existing quantity/BIM/work-package/constraint primitives; Progress and period contracts; Document/permit references; Risk/Issue/Change integration |
| Complejidad relativa | HIGH. Sin fechas, horas, costo o dotación comprometidos. |

# 6. O4 · CLAIMS / COMMISSIONING / HANDOVER / CLOSEOUT

Alcance: Claims/delay/forensic governed evidence; Mechanical completion/pre-commissioning/commissioning; Turnover/handover and operational readiness; Asset data transition; Project closeout without deleting canonical identity.

Dependencias: O1 retained baseline/current/update/period history; O2 contract/notice/document history; O3 applicable installed/quality/punch evidence; External accounting/asset boundary approved where needed.

| Elemento | Definición / control propuesto |
| --- | --- |
| Entrada | Complete source provenance and controlled historical snapshots; Distinct claim versus ordinary control transaction authority; System/package handover and residual condition acceptance policy approved |
| Salida / evidencia futura | Claim evidence/entitlement/quantum separated from controls source writes; Accepted commissioning/handover with unresolved conditions explicit; Financial/contract/schedule/document/claims closeout independently reconciled; Project operational closure approved while canonical Workspace/history retained |
| Riesgos | Forensic simulation contaminates live schedule; Handover mistaken for financial/legal closeout; External ERP/asset assumptions; Premature deletion/archive of identity or evidence |
| Reutilización | Existing claims/notices/impact primitives; Schedule import/version history; Documents/evidence register; Field/quality/work-package references |
| Complejidad relativa | VERY_HIGH. Sin fechas, horas, costo o dotación comprometidos. |

# 7. DAG de dependencias y ruta crítica de implementación

El grafo contiene 25 nodos y es acíclico. Representa contratos mínimos de implementación, no prohibición de realimentación transaccional. El grafo de operación sí permite Change↔Forecast y fuente↔reporting por revisiones controladas.

Cadena inicial: D01 → D14 mínimo → D02 → D03/D04 → D06/Change/Risk/Issue → D07 → D19. O2 consume O1; O3 requiere fuentes técnicas/materiales y QA/HSE aplicables antes de liberar Field; O4 requiere historia, aceptación técnica y condiciones residuales explícitas.

D04 no depende del hardening completo D12 para empezar: consume la autoridad Contract/PO existente en lectura y un contrato mínimo de semántica económica. D12 transaccional O2 depende de fuentes O1. Esta separación evita el ciclo falso Cost↔Contracts.

| ID / candidato | Prerrequisitos mínimos | Ola |
| --- | --- | --- |
| D01 Project Governance & Operational Setup | Raíz: identidad/autorización existente | O1 |
| D02 Scope Management | D01; D14 | O1 |
| D03 Schedule Management | D01; D02 | O1 |
| D04 Cost Management | D01; D02 | O1 |
| D05 Resource & Productivity Management | D02; D03; D04; D06 | O3 |
| D06 Progress Management | D02; D03; D04; D14 | O1 |
| D07 Forecast / ETC / EAC | D03; D04; D06; D08; D09; D10 | O1 |
| D08 Change Management | D02; D03; D04; D14 | O1 |
| D09 Risk Management | D01; D02; D14 | O1 |
| D10 Issue Management | D01; D14 | O1 |
| D11 Procurement Management | D02; D03; D04; D14 | O2 |
| D12 Commitments / Contract Administration | D01; D04; D11; D14 | O2 |
| D13 Engineering & Design Management | D02; D03; D14 | O2 |
| D14 Document & Information Management | D01 | O1 |
| D15 Interface Management | D10; D12; D13; D14 | O2 |
| D16 Construction / Field Management | D02; D03; D05; D06; D12; D13; D15; D17; D18 | O3 |
| D17 Quality Management | D02; D13; D14 | O3 |
| D18 HSE Management | D01; D09; D14 | O3 |
| D19 Project Controls & Reporting | D02; D03; D04; D06; D07; D08; D09; D10 | O1 |
| D20 Claims / Delay / Forensic Analysis | D03; D04; D08; D12; D14 | O4 |
| D21 Commissioning | D14; D16; D17; D18 | O4 |
| D22 Handover | D14; D21; D23 | O4 |
| D23 Operational Readiness | D01; D14; D17; D18; D21 | O4 |
| D24 Project Closeout | D03; D04; D12; D14; D20; D22; D25 | O4 |
| D25 Asset Handover / Transition | D01; D14; D22; D23 | O4 |

# 8. Priorización transparente y complejidad

Se valoran 25 candidatos × 11 criterios en escala entera 1–5. Son juicios arquitectónicos sujetos a discusión, no prioridades aprobadas por negocio ni ROI calculado. Urgencia=3 neutral en todos: no se inventó una preferencia del usuario.

Beneficios: valor, centralidad, reutilización, integración estratégica, aplicabilidad Owner/Contractor, reporting y urgencia. Penalizaciones: complejidad, riesgo de modelo y acoplamiento. Pesos propuestos suman 1; se muestran en la hoja 09 junto con 275 justificaciones y referencias.

Sea B la suma ponderada de beneficios y P la de penalizaciones; WB/WP son las sumas de sus pesos. Score=100×[(B−P)−(WB−5WP)]/[4(WB+WP)]. Con pesos válidos e inputs 1–5 el resultado va de 0 a 100. Vacíos, texto, decimales o fuera de rango se marcan inválidos y no generan score/rank.

Rank descendente admite empates sin fabricar desempate comercial. El score no salta prerequisites: identidad, autorización, SoD, fuente y período pueden imponer O1A aunque tenga alta complejidad. LOW/MEDIUM/HIGH/VERY_HIGH son complejidades relativas; no se traducen aquí a cronograma o presupuesto.

| Criterio | Peso | Sentido |
| --- | --- | --- |
| Valor de negocio | 15% | Beneficio |
| Centralidad | 15% | Beneficio |
| Reutilización | 10% | Beneficio |
| Complejidad | 10% | Penalización |
| Riesgo del modelo | 10% | Penalización |
| Acoplamiento | 10% | Penalización |
| Integración estratégica | 10% | Beneficio |
| Aplicabilidad Owner | 5% | Beneficio |
| Aplicabilidad Contractor | 5% | Beneficio |
| Valor de reporting | 5% | Beneficio |
| Urgencia declarada | 5% | Beneficio |

# 9. Matriz de riesgos y verificación futura

La implementación debe producir tests de caracterización y de contrato antes de alterar fuentes legacy. No se presentan pruebas ejecutadas en esta revisión estática. Los escenarios siguientes son criterios de salida futuros; no evidencia de funcionamiento actual.

| Riesgo | Escenarios de salida requeridos |
| --- | --- |
| Identidad / acceso | Tenant cruzado, mapping ausente/ambiguo, Workspace no activo, permiso revocado, concurrencia y replay; sin duplicar Project. |
| Autoridad estratégica | Owner con condición de compromiso vigente, fuente stale/revocada; Contractor/Direct autorizados sin requisito Owner indebido. |
| P6 / baseline | XML/XER subset, calendarios/unidades desconocidos, external links, Data Date, IDs reutilizados, diff/rechazo y rollback sin overwrite histórico. |
| Costo | Contract/PO included/call-off/additive, cancelación, certificado/recepción mismo origen, accrual/reversal, monedas y reserva una vez. |
| Progress / período | Métodos/denominadores distintos, aprobación independiente, corte/data date, cierre, late adjustment/reapertura y snapshot reproducible. |
| Change / Forecast | Aprobar ≠ implementar, receipts parciales/fallo, idempotencia, no baseline write; EAC/ETC bajo la misma base. |
| Reporting / documentos | GET sin comando oculto, mismo scope de fuentes, origen/version/hash y evidencia inaccesible no filtrada por export. |
| Compatibilidad | Rutas actuales y fuentes estratégicas sin regresión; formatos binarios no soportados rechazados explícitamente; no limpieza sin deprecación. |

# 10. Decisiones arquitectónicas y criterios de aceptación

ADR86–97 están PROPOSED_DESIGN, con aliases del prompt ADR-O-001–012 y evidencia path:line. No existe aprobación de negocio registrada para estas decisiones. Workbook 12_Decisions añade la clasificación de las 16 capacidades procurement/handoff.

Los 32 criterios siguientes se cubren como diseño documentado. PASS significa arquitectura definida y revisada en matrices/documentos, no software implementado, test de producto aprobado, validación jurídica ni signoff de negocio. Los tres criterios de protección se verifican además mediante huellas del producto y ausencia de migraciones.

| ID / criterio | Evidencia de diseño | Estado |
| --- | --- | --- |
| AC-01 Strategic → Operational boundary defined | H01–H15; master §2 | PASS de diseño |
| AC-02 Canonical Project identity preserved | ADR86; D01; GAP-01 | PASS de diseño |
| AC-03 Owner vs Contractor applicability defined | D01–D25 applicability; master §8 | PASS de diseño |
| AC-04 Project Controls integration core defined | ADR87; D19; master §6 | PASS de diseño |
| AC-05 Scope domain defined | D02; ADR90 | PASS de diseño |
| AC-06 Schedule domain defined | D03; ADR89 | PASS de diseño |
| AC-07 P6 boundary defined | ADR88; p6_manual_schedule_contract | PASS de diseño |
| AC-08 Cost domain defined | D04; baseline_and_budget_contract | PASS de diseño |
| AC-09 Progress architecture defined | D06; ADR91 | PASS de diseño |
| AC-10 Forecast architecture defined | D07; ADR93 | PASS de diseño |
| AC-11 Change architecture defined | D08; ADR92 | PASS de diseño |
| AC-12 Risk/Issue distinction defined | D09/D10; master §7 | PASS de diseño |
| AC-13 Procurement/Commitment duplication resolved conceptually | D11/D12; ADR94 | PASS de diseño |
| AC-14 Engineering boundary defined | D13 | PASS de diseño |
| AC-15 Construction boundary defined | D16; optional AWP | PASS de diseño |
| AC-16 Quality/HSE boundary defined | D17/D18 | PASS de diseño |
| AC-17 Claims boundary defined | D20 | PASS de diseño |
| AC-18 Commissioning/Handover boundary defined | D21–D25 | PASS de diseño |
| AC-19 ADMIN/USER matrix complete | 25-domain ADMIN/USER matrix | PASS de diseño |
| AC-20 Data ownership matrix complete | DO01–DO26 | PASS de diseño |
| AC-21 Integration matrix complete | IN01–IN26 | PASS de diseño |
| AC-22 Current capability inventory complete | BE15/FE25/PH16 evidence units | PASS de diseño |
| AC-23 Gap analysis complete | GAP-01–GAP-18 | PASS de diseño |
| AC-24 Legacy candidate inventory complete | 28 legacy evidence units; SAFE_TO_REMOVE0 | PASS de diseño |
| AC-25 Implementation waves defined | O1–O4 | PASS de diseño |
| AC-26 Wave dependency graph defined | 25-node acyclic DAG + O1A/B/C | PASS de diseño |
| AC-27 Wave O1 scope recommended | O1A prerequisite then O1B/C | PASS de diseño |
| AC-28 No new duplicate authority introduced | Single owner matrices; no product edits | PASS de diseño |
| AC-29 No operational CPM engine proposed | ADR88 | PASS de diseño |
| AC-30 No P6 API/direct sync proposed | ADR88 | PASS de diseño |
| AC-31 No strategic business rule silently changed | Product SHA baseline/final audit | PASS de diseño |
| AC-32 No broad migration created | Product SHA baseline/final audit | PASS de diseño |

# 11. Único siguiente prompt recomendado

WAVE O1 — PROJECT CONTROLS FOUNDATION.

Implementar O1 comenzando exclusivamente por O1A: reutilizar Enterprise Workspace PROJECT y sus lifecycle/RBAC; diseñar y validar binding explícito con el agregado operacional legacy, sin crear otro Project master ni asumir IDs iguales; mantener las tres rutas de autorización y condiciones actuales. Reutilizar evidencia/versiones y establecer período/políticas comunes ADMIN/USER, con SoD, idempotencia, concurrencia y auditoría. Preservar toda lógica estratégica e historia aprobada.

Cerrar O1A con pruebas de identidad, acceso, colisiones, estado, currentness, condiciones y ciclo de período; solo entonces habilitar O1B baselines/adapters de Scope/Schedule/Cost/Progress/Change/Risk/Issue y O1C Forecast/Reporting bajo alcance autorizado. P6 sigue externo manual XML/XER, sin CPM/API/sync. No ampliar a O2–O4. Entregar evidencia, inventario de reutilización y reporte técnico; no declarar liberación ni signoff sin aprobación autorizada.

STOP: la tarea actual termina en este diseño. La siguiente implementación requiere instrucción expresa.

Referencias principales: Master Architecture.docx; Domain Map and Roadmap.xlsx; docs/architecture/operational/architecture-data.json; inventarios y auditorías del corte 20261019. Oracle P6 y CII se citan en el informe maestro para las fronteras XML/XER y AWP.